## Merge
Activity ID | HOUSE | TASK | START | Duration | End | Resource | Number | Cost
1 | 1 | Concrete floor | 2020-02-15 | 40 | 2020-03-25 | Concreters | 2 | 100
1 | 1 | Concrete floor | 2020-02-15 | 40 | 2020-03-25 | Ready-mix concrete | 100 | 2
2 | 1 | Build walls | 2020-02-19 | 3 | 2020-02-21 | Builders | 4 | 90
3 | 1 | Build interior | 2020-02-22 | 5 | 2020-02-26 | Builders | 2 | 90
3 | 1 | Build interior | 2020-02-22 | 5 | 2020-02-26 | Decorators | 3 | 50
4 | 1 | Fit out | 2020-02-27 | 7 | 2020-03-04 | Decorators | 5 | 50
4 | 1 | Fit out | 2020-02-27 | 7 | 2020-03-04 | Mechanical and Electrical | 6 | 80
5 | 1 | Build roof | 2020-02-20 | 3 | 2020-02-22 | Builders | 2 | 90
5 | 1 | Build roof | 2020-02-20 | 3 | 2020-02-22 | Mobile crane | 1 | 150
6 | 2 | Concrete floor | 2020-02-29 | 40 | 2020-04-08 | Concreters | 3 | 100
6 | 2 | Concrete floor | 2020-02-29 | 40 | 2020-04-08 | Ready-mix concrete | 100 | 2
7 | 2 | Build walls | 2020-03-04 | 3 | 2020-03-06 | Builders | 4 | 90
8 | 2 | Build interior | 2020-03-07 | 5 | 2020-03-11 | Builders | 2 | 90
8 | 2 | Build interior | 2020-03-07 | 5 | 2020-03-11 | Decorators | 2 | 50
9 | 2 | Fit out | 2020-03-12 | 7 | 2020-03-18 | Decorators | 6 | 50
9 | 2 | Fit out | 2020-03-12 | 7 | 2020-03-18 | Mechanical and Electrical | 7 | 80
10 | 2 | Build roof | 2020-03-05 | 3 | 2020-03-07 | Builders | 2 | 90
10 | 2 | Build roof | 2020-03-05 | 3 | 2020-03-07 | Mobile crane | 2 | 150
11 | 3 | Concrete floor | 2020-03-14 | 40 | 2020-04-22 | Concreters | 3 | 100
11 | 3 | Concrete floor | 2020-03-14 | 40 | 2020-04-22 | Ready-mix concrete | 100 | 2
12 | 3 | Build walls | 2020-03-18 | 3 | 2020-03-20 | Builders | 5 | 90
13 | 3 | Build interior | 2020-03-21 | 5 | 2020-03-25 | Builders | 2 | 90
13 | 3 | Build interior | 2020-03-21 | 5 | 2020-03-25 | Decorators | 4 | 50
14 | 3 | Fit out | 2020-03-26 | 7 | 2020-04-01 | Decorators | 4 | 50
14 | 3 | Fit out | 2020-03-26 | 7 | 2020-04-01 | Mechanical and Electrical | 7 | 80
15 | 3 | Build roof | 2020-03-19 | 3 | 2020-03-21 | Builders | 1 | 90
16 | 4 | Concrete floor | 2020-03-28 | 40 | 2020-05-06 | Concreters | 2 | 100
16 | 4 | Concrete floor | 2020-03-28 | 40 | 2020-05-06 | Ready-mix concrete | 100 | 2
17 | 4 | Build walls | 2020-04-01 | 3 | 2020-04-03 | Builders | 3 | 90
18 | 4 | Build interior | 2020-04-04 | 5 | 2020-04-08 | Builders | 2 | 90
18 | 4 | Build interior | 2020-04-04 | 5 | 2020-04-08 | Decorators | 4 | 50
19 | 4 | Fit out | 2020-04-09 | 7 | 2020-04-15 | Decorators | 6 | 50
19 | 4 | Fit out | 2020-04-09 | 7 | 2020-04-15 | Mechanical and Electrical | 5 | 80
20 | 4 | Build roof | 2020-04-02 | 3 | 2020-04-04 | Builders | 1 | 90
21 | 5 | Concrete floor | 2020-04-11 | 40 | 2020-05-20 | Concreters | 3 | 100
21 | 5 | Concrete floor | 2020-04-11 | 40 | 2020-05-20 | Ready-mix concrete | 100 | 2
22 | 5 | Build walls | 2020-04-15 | 3 | 2020-04-17 | Builders | 3 | 90
23 | 5 | Build interior | 2020-04-18 | 5 | 2020-04-22 | Builders | 3 | 90
23 | 5 | Build interior | 2020-04-18 | 5 | 2020-04-22 | Decorators | 2 | 50
24 | 5 | Fit out | 2020-04-23 | 7 | 2020-04-29 | Decorators | 4 | 50
24 | 5 | Fit out | 2020-04-23 | 7 | 2020-04-29 | Mechanical and Electrical | 6 | 80
25 | 5 | Build roof | 2020-04-16 | 3 | 2020-04-18 | Builders | 2 | 90
25 | 5 | Build roof | 2020-04-16 | 3 | 2020-04-18 | Mobile crane | 2 | 150
26 | 6 | Concrete floor | 2020-04-25 | 40 | 2020-06-03 | Concreters | 2 | 100
26 | 6 | Concrete floor | 2020-04-25 | 40 | 2020-06-03 | Ready-mix concrete | 100 | 2
27 | 6 | Build walls | 2020-04-29 | 3 | 2020-05-01 | Builders | 5 | 90
28 | 6 | Build interior | 2020-05-02 | 5 | 2020-05-06 | Builders | 2 | 90
28 | 6 | Build interior | 2020-05-02 | 5 | 2020-05-06 | Decorators | 3 | 50
29 | 6 | Fit out | 2020-05-07 | 7 | 2020-05-13 | Decorators | 6 | 50
29 | 6 | Fit out | 2020-05-07 | 7 | 2020-05-13 | Mechanical and Electrical | 5 | 80
30 | 6 | Build roof | 2020-04-30 | 3 | 2020-05-02 | Builders | 1 | 90
31 | 7 | Concrete floor | 2020-05-09 | 40 | 2020-06-17 | Concreters | 2 | 100
31 | 7 | Concrete floor | 2020-05-09 | 40 | 2020-06-17 | Ready-mix concrete | 100 | 2
32 | 7 | Build walls | 2020-05-13 | 3 | 2020-05-15 | Builders | 4 | 90
33 | 7 | Build interior | 2020-05-16 | 5 | 2020-05-20 | Builders | 2 | 90
33 | 7 | Build interior | 2020-05-16 | 5 | 2020-05-20 | Decorators | 4 | 50
34 | 7 | Fit out | 2020-05-21 | 7 | 2020-05-27 | Decorators | 4 | 50
34 | 7 | Fit out | 2020-05-21 | 7 | 2020-05-27 | Mechanical and Electrical | 6 | 80
35 | 7 | Build roof | 2020-05-14 | 3 | 2020-05-16 | Builders | 2 | 90
35 | 7 | Build roof | 2020-05-14 | 3 | 2020-05-16 | Mobile crane | 1 | 150
36 | 8 | Concrete floor | 2020-05-23 | 40 | 2020-07-01 | Concreters | 3 | 100
36 | 8 | Concrete floor | 2020-05-23 | 40 | 2020-07-01 | Ready-mix concrete | 100 | 2
37 | 8 | Build walls | 2020-05-27 | 3 | 2020-05-29 | Builders | 3 | 90
38 | 8 | Build interior | 2020-05-30 | 5 | 2020-06-03 | Builders | 1 | 90
38 | 8 | Build interior | 2020-05-30 | 5 | 2020-06-03 | Decorators | 2 | 50
39 | 8 | Fit out | 2020-06-04 | 7 | 2020-06-10 | Decorators | 4 | 50
39 | 8 | Fit out | 2020-06-04 | 7 | 2020-06-10 | Mechanical and Electrical | 7 | 80
40 | 8 | Build roof | 2020-05-28 | 3 | 2020-05-30 | Builders | 1 | 90
41 | 9 | Concrete floor | 2020-06-06 | 40 | 2020-07-15 | Concreters | 1 | 100
41 | 9 | Concrete floor | 2020-06-06 | 40 | 2020-07-15 | Ready-mix concrete | 100 | 2
42 | 9 | Build walls | 2020-06-10 | 3 | 2020-06-12 | Builders | 5 | 90
43 | 9 | Build interior | 2020-06-13 | 5 | 2020-06-17 | Builders | 3 | 90
43 | 9 | Build interior | 2020-06-13 | 5 | 2020-06-17 | Decorators | 2 | 50
44 | 9 | Fit out | 2020-06-18 | 7 | 2020-06-24 | Decorators | 5 | 50
44 | 9 | Fit out | 2020-06-18 | 7 | 2020-06-24 | Mechanical and Electrical | 5 | 80
45 | 9 | Build roof | 2020-06-11 | 3 | 2020-06-13 | Builders | 3 | 90
45 | 9 | Build roof | 2020-06-11 | 3 | 2020-06-13 | Mobile crane | 2 | 150
46 | 10 | Concrete floor | 2020-06-20 | 40 | 2020-07-29 | Concreters | 2 | 100
46 | 10 | Concrete floor | 2020-06-20 | 40 | 2020-07-29 | Ready-mix concrete | 100 | 2
47 | 10 | Build walls | 2020-06-24 | 3 | 2020-06-26 | Builders | 4 | 90
48 | 10 | Build interior | 2020-06-27 | 5 | 2020-07-01 | Builders | 1 | 90
48 | 10 | Build interior | 2020-06-27 | 5 | 2020-07-01 | Decorators | 3 | 50
49 | 10 | Fit out | 2020-07-02 | 7 | 2020-07-08 | Decorators | 5 | 50
49 | 10 | Fit out | 2020-07-02 | 7 | 2020-07-08 | Mechanical and Electrical | 5 | 80
50 | 10 | Build roof | 2020-06-25 | 3 | 2020-06-27 | Builders | 1 | 90
50 | 10 | Build roof | 2020-06-25 | 3 | 2020-06-27 | Mobile crane | 2 | 150
51 | 11 | Concrete floor | 2020-07-04 | 40 | 2020-08-12 | Concreters | 3 | 100
51 | 11 | Concrete floor | 2020-07-04 | 40 | 2020-08-12 | Ready-mix concrete | 100 | 2
52 | 11 | Build walls | 2020-07-08 | 3 | 2020-07-10 | Builders | 5 | 90
53 | 11 | Build interior | 2020-07-11 | 5 | 2020-07-15 | Builders | 2 | 90
53 | 11 | Build interior | 2020-07-11 | 5 | 2020-07-15 | Decorators | 4 | 50
54 | 11 | Fit out | 2020-07-16 | 7 | 2020-07-22 | Decorators | 5 | 50
54 | 11 | Fit out | 2020-07-16 | 7 | 2020-07-22 | Mechanical and Electrical | 5 | 80
55 | 11 | Build roof | 2020-07-09 | 3 | 2020-07-11 | Builders | 2 | 90
55 | 11 | Build roof | 2020-07-09 | 3 | 2020-07-11 | Mobile crane | 2 | 150
56 | 12 | Concrete floor | 2020-07-18 | 40 | 2020-08-26 | Concreters | 3 | 100
56 | 12 | Concrete floor | 2020-07-18 | 40 | 2020-08-26 | Ready-mix concrete | 100 | 2
57 | 12 | Build walls | 2020-07-22 | 3 | 2020-07-24 | Builders | 4 | 90
58 | 12 | Build interior | 2020-07-25 | 5 | 2020-07-29 | Builders | 1 | 90
58 | 12 | Build interior | 2020-07-25 | 5 | 2020-07-29 | Decorators | 4 | 50
59 | 12 | Fit out | 2020-07-30 | 7 | 2020-08-05 | Decorators | 6 | 50
59 | 12 | Fit out | 2020-07-30 | 7 | 2020-08-05 | Mechanical and Electrical | 6 | 80
60 | 12 | Build roof | 2020-07-23 | 3 | 2020-07-25 | Builders | 2 | 90
61 | 13 | Concrete floor | 2020-08-01 | 40 | 2020-09-09 | Concreters | 1 | 100
61 | 13 | Concrete floor | 2020-08-01 | 40 | 2020-09-09 | Ready-mix concrete | 100 | 2
62 | 13 | Build walls | 2020-08-05 | 3 | 2020-08-07 | Builders | 3 | 90
63 | 13 | Build interior | 2020-08-08 | 5 | 2020-08-12 | Builders | 3 | 90
63 | 13 | Build interior | 2020-08-08 | 5 | 2020-08-12 | Decorators | 3 | 50
64 | 13 | Fit out | 2020-08-13 | 7 | 2020-08-19 | Decorators | 4 | 50
64 | 13 | Fit out | 2020-08-13 | 7 | 2020-08-19 | Mechanical and Electrical | 7 | 80
65 | 13 | Build roof | 2020-08-06 | 3 | 2020-08-08 | Builders | 3 | 90
65 | 13 | Build roof | 2020-08-06 | 3 | 2020-08-08 | Mobile crane | 1 | 150
66 | 14 | Concrete floor | 2020-08-15 | 40 | 2020-09-23 | Concreters | 1 | 100
66 | 14 | Concrete floor | 2020-08-15 | 40 | 2020-09-23 | Ready-mix concrete | 100 | 2
67 | 14 | Build walls | 2020-08-19 | 3 | 2020-08-21 | Builders | 3 | 90
68 | 14 | Build interior | 2020-08-22 | 5 | 2020-08-26 | Builders | 3 | 90
68 | 14 | Build interior | 2020-08-22 | 5 | 2020-08-26 | Decorators | 4 | 50
69 | 14 | Fit out | 2020-08-27 | 7 | 2020-09-02 | Decorators | 6 | 50
69 | 14 | Fit out | 2020-08-27 | 7 | 2020-09-02 | Mechanical and Electrical | 7 | 80
70 | 14 | Build roof | 2020-08-20 | 3 | 2020-08-22 | Builders | 3 | 90
70 | 14 | Build roof | 2020-08-20 | 3 | 2020-08-22 | Mobile crane | 1 | 150
71 | 15 | Concrete floor | 2020-08-29 | 40 | 2020-10-07 | Concreters | 1 | 100
71 | 15 | Concrete floor | 2020-08-29 | 40 | 2020-10-07 | Ready-mix concrete | 100 | 2
72 | 15 | Build walls | 2020-09-02 | 3 | 2020-09-04 | Builders | 4 | 90
73 | 15 | Build interior | 2020-09-05 | 5 | 2020-09-09 | Builders | 1 | 90
73 | 15 | Build interior | 2020-09-05 | 5 | 2020-09-09 | Decorators | 4 | 50
74 | 15 | Fit out | 2020-09-10 | 7 | 2020-09-16 | Decorators | 5 | 50
74 | 15 | Fit out | 2020-09-10 | 7 | 2020-09-16 | Mechanical and Electrical | 6 | 80
75 | 15 | Build roof | 2020-09-03 | 3 | 2020-09-05 | Builders | 1 | 90
75 | 15 | Build roof | 2020-09-03 | 3 | 2020-09-05 | Mobile crane | 2 | 150
76 | 16 | Concrete floor | 2020-09-12 | 40 | 2020-10-21 | Concreters | 3 | 100
76 | 16 | Concrete floor | 2020-09-12 | 40 | 2020-10-21 | Ready-mix concrete | 100 | 2
77 | 16 | Build walls | 2020-09-16 | 3 | 2020-09-18 | Builders | 4 | 90
78 | 16 | Build interior | 2020-09-19 | 5 | 2020-09-23 | Builders | 1 | 90
78 | 16 | Build interior | 2020-09-19 | 5 | 2020-09-23 | Decorators | 2 | 50
79 | 16 | Fit out | 2020-09-24 | 7 | 2020-09-30 | Decorators | 5 | 50
79 | 16 | Fit out | 2020-09-24 | 7 | 2020-09-30 | Mechanical and Electrical | 6 | 80
80 | 16 | Build roof | 2020-09-17 | 3 | 2020-09-19 | Builders | 1 | 90
81 | 17 | Concrete floor | 2020-09-26 | 40 | 2020-11-04 | Concreters | 2 | 100
81 | 17 | Concrete floor | 2020-09-26 | 40 | 2020-11-04 | Ready-mix concrete | 100 | 2
82 | 17 | Build walls | 2020-09-30 | 3 | 2020-10-02 | Builders | 3 | 90
83 | 17 | Build interior | 2020-10-03 | 5 | 2020-10-07 | Builders | 3 | 90
83 | 17 | Build interior | 2020-10-03 | 5 | 2020-10-07 | Decorators | 3 | 50
84 | 17 | Fit out | 2020-10-08 | 7 | 2020-10-14 | Decorators | 5 | 50
84 | 17 | Fit out | 2020-10-08 | 7 | 2020-10-14 | Mechanical and Electrical | 6 | 80
85 | 17 | Build roof | 2020-10-01 | 3 | 2020-10-03 | Builders | 1 | 90
85 | 17 | Build roof | 2020-10-01 | 3 | 2020-10-03 | Mobile crane | 2 | 150
86 | 18 | Concrete floor | 2020-10-10 | 40 | 2020-11-18 | Concreters | 3 | 100
86 | 18 | Concrete floor | 2020-10-10 | 40 | 2020-11-18 | Ready-mix concrete | 100 | 2
87 | 18 | Build walls | 2020-10-14 | 3 | 2020-10-16 | Builders | 4 | 90
88 | 18 | Build interior | 2020-10-17 | 5 | 2020-10-21 | Builders | 2 | 90
88 | 18 | Build interior | 2020-10-17 | 5 | 2020-10-21 | Decorators | 2 | 50
89 | 18 | Fit out | 2020-10-22 | 7 | 2020-10-28 | Decorators | 4 | 50
89 | 18 | Fit out | 2020-10-22 | 7 | 2020-10-28 | Mechanical and Electrical | 6 | 80
90 | 18 | Build roof | 2020-10-15 | 3 | 2020-10-17 | Builders | 2 | 90
91 | 19 | Concrete floor | 2020-10-24 | 40 | 2020-12-02 | Concreters | 2 | 100
91 | 19 | Concrete floor | 2020-10-24 | 40 | 2020-12-02 | Ready-mix concrete | 100 | 2
92 | 19 | Build walls | 2020-10-28 | 3 | 2020-10-30 | Builders | 5 | 90
93 | 19 | Build interior | 2020-10-31 | 5 | 2020-11-04 | Builders | 3 | 90
93 | 19 | Build interior | 2020-10-31 | 5 | 2020-11-04 | Decorators | 3 | 50
94 | 19 | Fit out | 2020-11-05 | 7 | 2020-11-11 | Decorators | 4 | 50
94 | 19 | Fit out | 2020-11-05 | 7 | 2020-11-11 | Mechanical and Electrical | 6 | 80
95 | 19 | Build roof | 2020-10-29 | 3 | 2020-10-31 | Builders | 2 | 90
96 | 20 | Concrete floor | 2020-11-07 | 40 | 2020-12-16 | Concreters | 2 | 100
96 | 20 | Concrete floor | 2020-11-07 | 40 | 2020-12-16 | Ready-mix concrete | 100 | 2
97 | 20 | Build walls | 2020-11-11 | 3 | 2020-11-13 | Builders | 5 | 90
98 | 20 | Build interior | 2020-11-14 | 5 | 2020-11-18 | Builders | 1 | 90
98 | 20 | Build interior | 2020-11-14 | 5 | 2020-11-18 | Decorators | 4 | 50
99 | 20 | Fit out | 2020-11-19 | 7 | 2020-11-25 | Decorators | 6 | 50
99 | 20 | Fit out | 2020-11-19 | 7 | 2020-11-25 | Mechanical and Electrical | 6 | 80
100 | 20 | Build roof | 2020-11-12 | 3 | 2020-11-14 | Builders | 3 | 90
100 | 20 | Build roof | 2020-11-12 | 3 | 2020-11-14 | Mobile crane | 1 | 150
101 | 21 | Concrete floor | 2020-11-21 | 40 | 2020-12-30 | Concreters | 2 | 100
101 | 21 | Concrete floor | 2020-11-21 | 40 | 2020-12-30 | Ready-mix concrete | 100 | 2
102 | 21 | Build walls | 2020-11-25 | 3 | 2020-11-27 | Builders | 3 | 90
103 | 21 | Build interior | 2020-11-28 | 5 | 2020-12-02 | Builders | 1 | 90
103 | 21 | Build interior | 2020-11-28 | 5 | 2020-12-02 | Decorators | 2 | 50
104 | 21 | Fit out | 2020-12-03 | 7 | 2020-12-09 | Decorators | 6 | 50
104 | 21 | Fit out | 2020-12-03 | 7 | 2020-12-09 | Mechanical and Electrical | 7 | 80
105 | 21 | Build roof | 2020-11-26 | 3 | 2020-11-28 | Builders | 3 | 90
105 | 21 | Build roof | 2020-11-26 | 3 | 2020-11-28 | Mobile crane | 1 | 150
106 | 22 | Concrete floor | 2020-12-05 | 40 | 2021-01-13 | Concreters | 2 | 100
106 | 22 | Concrete floor | 2020-12-05 | 40 | 2021-01-13 | Ready-mix concrete | 100 | 2
107 | 22 | Build walls | 2020-12-09 | 3 | 2020-12-11 | Builders | 4 | 90
108 | 22 | Build interior | 2020-12-12 | 5 | 2020-12-16 | Builders | 1 | 90
108 | 22 | Build interior | 2020-12-12 | 5 | 2020-12-16 | Decorators | 4 | 50
109 | 22 | Fit out | 2020-12-17 | 7 | 2020-12-23 | Decorators | 5 | 50
109 | 22 | Fit out | 2020-12-17 | 7 | 2020-12-23 | Mechanical and Electrical | 7 | 80
110 | 22 | Build roof | 2020-12-10 | 3 | 2020-12-12 | Builders | 3 | 90
110 | 22 | Build roof | 2020-12-10 | 3 | 2020-12-12 | Mobile crane | 1 | 150
111 | 23 | Concrete floor | 2020-12-19 | 40 | 2021-01-27 | Concreters | 1 | 100
111 | 23 | Concrete floor | 2020-12-19 | 40 | 2021-01-27 | Ready-mix concrete | 100 | 2
112 | 23 | Build walls | 2020-12-23 | 3 | 2020-12-25 | Builders | 4 | 90
113 | 23 | Build interior | 2020-12-26 | 5 | 2020-12-30 | Builders | 1 | 90
113 | 23 | Build interior | 2020-12-26 | 5 | 2020-12-30 | Decorators | 4 | 50
114 | 23 | Fit out | 2020-12-31 | 7 | 2021-01-06 | Decorators | 5 | 50
114 | 23 | Fit out | 2020-12-31 | 7 | 2021-01-06 | Mechanical and Electrical | 7 | 80
115 | 23 | Build roof | 2020-12-24 | 3 | 2020-12-26 | Builders | 3 | 90
115 | 23 | Build roof | 2020-12-24 | 3 | 2020-12-26 | Mobile crane | 1 | 150
116 | 24 | Concrete floor | 2021-01-02 | 40 | 2021-02-10 | Concreters | 2 | 100
116 | 24 | Concrete floor | 2021-01-02 | 40 | 2021-02-10 | Ready-mix concrete | 100 | 2
117 | 24 | Build walls | 2021-01-06 | 3 | 2021-01-08 | Builders | 3 | 90
118 | 24 | Build interior | 2021-01-09 | 5 | 2021-01-13 | Builders | 2 | 90
118 | 24 | Build interior | 2021-01-09 | 5 | 2021-01-13 | Decorators | 2 | 50
119 | 24 | Fit out | 2021-01-14 | 7 | 2021-01-20 | Decorators | 4 | 50
119 | 24 | Fit out | 2021-01-14 | 7 | 2021-01-20 | Mechanical and Electrical | 5 | 80
120 | 24 | Build roof | 2021-01-07 | 3 | 2021-01-09 | Builders | 2 | 90
121 | 25 | Concrete floor | 2021-01-16 | 40 | 2021-02-24 | Concreters | 3 | 100
121 | 25 | Concrete floor | 2021-01-16 | 40 | 2021-02-24 | Ready-mix concrete | 100 | 2
122 | 25 | Build walls | 2021-01-20 | 3 | 2021-01-22 | Builders | 4 | 90
123 | 25 | Build interior | 2021-01-23 | 5 | 2021-01-27 | Builders | 1 | 90
123 | 25 | Build interior | 2021-01-23 | 5 | 2021-01-27 | Decorators | 4 | 50
124 | 25 | Fit out | 2021-01-28 | 7 | 2021-02-03 | Decorators | 6 | 50
124 | 25 | Fit out | 2021-01-28 | 7 | 2021-02-03 | Mechanical and Electrical | 5 | 80
125 | 25 | Build roof | 2021-01-21 | 3 | 2021-01-23 | Builders | 3 | 90
126 | 26 | Concrete floor | 2021-01-30 | 40 | 2021-03-10 | Concreters | 2 | 100
126 | 26 | Concrete floor | 2021-01-30 | 40 | 2021-03-10 | Ready-mix concrete | 100 | 2
127 | 26 | Build walls | 2021-02-03 | 3 | 2021-02-05 | Builders | 4 | 90
128 | 26 | Build interior | 2021-02-06 | 5 | 2021-02-10 | Builders | 3 | 90
128 | 26 | Build interior | 2021-02-06 | 5 | 2021-02-10 | Decorators | 3 | 50
129 | 26 | Fit out | 2021-02-11 | 7 | 2021-02-17 | Decorators | 4 | 50
129 | 26 | Fit out | 2021-02-11 | 7 | 2021-02-17 | Mechanical and Electrical | 7 | 80
130 | 26 | Build roof | 2021-02-04 | 3 | 2021-02-06 | Builders | 1 | 90
130 | 26 | Build roof | 2021-02-04 | 3 | 2021-02-06 | Mobile crane | 1 | 150
131 | 27 | Concrete floor | 2021-02-13 | 40 | 2021-03-24 | Concreters | 3 | 100
131 | 27 | Concrete floor | 2021-02-13 | 40 | 2021-03-24 | Ready-mix concrete | 100 | 2
132 | 27 | Build walls | 2021-02-17 | 3 | 2021-02-19 | Builders | 4 | 90
133 | 27 | Build interior | 2021-02-20 | 5 | 2021-02-24 | Builders | 3 | 90
133 | 27 | Build interior | 2021-02-20 | 5 | 2021-02-24 | Decorators | 2 | 50
134 | 27 | Fit out | 2021-02-25 | 7 | 2021-03-03 | Decorators | 6 | 50
134 | 27 | Fit out | 2021-02-25 | 7 | 2021-03-03 | Mechanical and Electrical | 6 | 80
135 | 27 | Build roof | 2021-02-18 | 3 | 2021-02-20 | Builders | 2 | 90
135 | 27 | Build roof | 2021-02-18 | 3 | 2021-02-20 | Mobile crane | 1 | 150
136 | 28 | Concrete floor | 2021-02-27 | 40 | 2021-04-07 | Concreters | 2 | 100
136 | 28 | Concrete floor | 2021-02-27 | 40 | 2021-04-07 | Ready-mix concrete | 100 | 2
137 | 28 | Build walls | 2021-03-03 | 3 | 2021-03-05 | Builders | 3 | 90
138 | 28 | Build interior | 2021-03-06 | 5 | 2021-03-10 | Builders | 2 | 90
138 | 28 | Build interior | 2021-03-06 | 5 | 2021-03-10 | Decorators | 3 | 50
139 | 28 | Fit out | 2021-03-11 | 7 | 2021-03-17 | Decorators | 4 | 50
139 | 28 | Fit out | 2021-03-11 | 7 | 2021-03-17 | Mechanical and Electrical | 6 | 80
140 | 28 | Build roof | 2021-03-04 | 3 | 2021-03-06 | Builders | 2 | 90
141 | 29 | Concrete floor | 2021-03-13 | 40 | 2021-04-21 | Concreters | 2 | 100
141 | 29 | Concrete floor | 2021-03-13 | 40 | 2021-04-21 | Ready-mix concrete | 100 | 2
142 | 29 | Build walls | 2021-03-17 | 3 | 2021-03-19 | Builders | 3 | 90
143 | 29 | Build interior | 2021-03-20 | 5 | 2021-03-24 | Builders | 3 | 90
143 | 29 | Build interior | 2021-03-20 | 5 | 2021-03-24 | Decorators | 2 | 50
144 | 29 | Fit out | 2021-03-25 | 7 | 2021-03-31 | Decorators | 4 | 50
144 | 29 | Fit out | 2021-03-25 | 7 | 2021-03-31 | Mechanical and Electrical | 6 | 80
145 | 29 | Build roof | 2021-03-18 | 3 | 2021-03-20 | Builders | 1 | 90
145 | 29 | Build roof | 2021-03-18 | 3 | 2021-03-20 | Builders | 1 | 90
145 | 29 | Build roof | 2021-03-18 | 3 | 2021-03-20 | Builders | 1 | 90
145 | 29 | Build roof | 2021-03-18 | 3 | 2021-03-20 | Mobile crane | 1 | 150
146 | 30 | Concrete floor | 2021-03-27 | 40 | 2021-05-05 | Concreters | 2 | 100
146 | 30 | Concrete floor | 2021-03-27 | 40 | 2021-05-05 | Ready-mix concrete | 100 | 2
147 | 30 | Build walls | 2021-03-31 | 3 | 2021-04-02 | Builders | 4 | 90
148 | 30 | Build interior | 2021-04-03 | 5 | 2021-04-07 | Builders | 3 | 90
148 | 30 | Build interior | 2021-04-03 | 5 | 2021-04-07 | Decorators | 2 | 50
149 | 30 | Fit out | 2021-04-08 | 7 | 2021-04-14 | Decorators | 5 | 50
149 | 30 | Fit out | 2021-04-08 | 7 | 2021-04-14 | Mechanical and Electrical | 6 | 80
150 | 30 | Build roof | 2021-04-01 | 3 | 2021-04-03 | Builders | 2 | 90
150 | 30 | Build roof | 2021-04-01 | 3 | 2021-04-03 | Mobile crane | 2 | 150
151 | 31 | Concrete floor | 2021-04-10 | 40 | 2021-05-19 | Concreters | 1 | 100
151 | 31 | Concrete floor | 2021-04-10 | 40 | 2021-05-19 | Ready-mix concrete | 100 | 2
152 | 31 | Build walls | 2021-04-14 | 3 | 2021-04-16 | Builders | 5 | 90
153 | 31 | Build interior | 2021-04-17 | 5 | 2021-04-21 | Builders | 1 | 90
153 | 31 | Build interior | 2021-04-17 | 5 | 2021-04-21 | Decorators | 3 | 50
154 | 31 | Fit out | 2021-04-22 | 7 | 2021-04-28 | Decorators | 4 | 50
154 | 31 | Fit out | 2021-04-22 | 7 | 2021-04-28 | Mechanical and Electrical | 7 | 80
155 | 31 | Build roof | 2021-04-15 | 3 | 2021-04-17 | Builders | 2 | 90
156 | 32 | Concrete floor | 2021-04-24 | 40 | 2021-06-02 | Concreters | 1 | 100
156 | 32 | Concrete floor | 2021-04-24 | 40 | 2021-06-02 | Ready-mix concrete | 100 | 2
157 | 32 | Build walls | 2021-04-28 | 3 | 2021-04-30 | Builders | 4 | 90
158 | 32 | Build interior | 2021-05-01 | 5 | 2021-05-05 | Builders | 1 | 90
158 | 32 | Build interior | 2021-05-01 | 5 | 2021-05-05 | Decorators | 3 | 50
159 | 32 | Fit out | 2021-05-06 | 7 | 2021-05-12 | Decorators | 5 | 50
159 | 32 | Fit out | 2021-05-06 | 7 | 2021-05-12 | Mechanical and Electrical | 6 | 80
160 | 32 | Build roof | 2021-04-29 | 3 | 2021-05-01 | Builders | 2 | 90
161 | 33 | Concrete floor | 2021-05-08 | 40 | 2021-06-16 | Concreters | 1 | 100
161 | 33 | Concrete floor | 2021-05-08 | 40 | 2021-06-16 | Ready-mix concrete | 100 | 2
162 | 33 | Build walls | 2021-05-12 | 3 | 2021-05-14 | Builders | 5 | 90
163 | 33 | Build interior | 2021-05-15 | 5 | 2021-05-19 | Builders | 1 | 90
163 | 33 | Build interior | 2021-05-15 | 5 | 2021-05-19 | Decorators | 2 | 50
164 | 33 | Fit out | 2021-05-20 | 7 | 2021-05-26 | Decorators | 6 | 50
164 | 33 | Fit out | 2021-05-20 | 7 | 2021-05-26 | Mechanical and Electrical | 6 | 80
165 | 33 | Build roof | 2021-05-13 | 3 | 2021-05-15 | Builders | 1 | 90
165 | 33 | Build roof | 2021-05-13 | 3 | 2021-05-15 | Mobile crane | 2 | 150
166 | 34 | Concrete floor | 2021-05-22 | 40 | 2021-06-30 | Concreters | 1 | 100
166 | 34 | Concrete floor | 2021-05-22 | 40 | 2021-06-30 | Ready-mix concrete | 100 | 2
167 | 34 | Build walls | 2021-05-26 | 3 | 2021-05-28 | Builders | 3 | 90
168 | 34 | Build interior | 2021-05-29 | 5 | 2021-06-02 | Builders | 1 | 90
168 | 34 | Build interior | 2021-05-29 | 5 | 2021-06-02 | Decorators | 4 | 50
169 | 34 | Fit out | 2021-06-03 | 7 | 2021-06-09 | Decorators | 6 | 50
169 | 34 | Fit out | 2021-06-03 | 7 | 2021-06-09 | Mechanical and Electrical | 7 | 80
170 | 34 | Build roof | 2021-05-27 | 3 | 2021-05-29 | Builders | 2 | 90
170 | 34 | Build roof | 2021-05-27 | 3 | 2021-05-29 | Mobile crane | 1 | 150
171 | 35 | Concrete floor | 2021-06-05 | 40 | 2021-07-14 | Concreters | 2 | 100
171 | 35 | Concrete floor | 2021-06-05 | 40 | 2021-07-14 | Ready-mix concrete | 100 | 2
172 | 35 | Build walls | 2021-06-09 | 3 | 2021-06-11 | Builders | 4 | 90
173 | 35 | Build interior | 2021-06-12 | 5 | 2021-06-16 | Builders | 1 | 90
173 | 35 | Build interior | 2021-06-12 | 5 | 2021-06-16 | Decorators | 3 | 50
174 | 35 | Fit out | 2021-06-17 | 7 | 2021-06-23 | Decorators | 6 | 50
174 | 35 | Fit out | 2021-06-17 | 7 | 2021-06-23 | Mechanical and Electrical | 5 | 80
175 | 35 | Build roof | 2021-06-10 | 3 | 2021-06-12 | Builders | 3 | 90
176 | 36 | Concrete floor | 2021-06-19 | 40 | 2021-07-28 | Concreters | 3 | 100
176 | 36 | Concrete floor | 2021-06-19 | 40 | 2021-07-28 | Ready-mix concrete | 100 | 2
177 | 36 | Build walls | 2021-06-23 | 3 | 2021-06-25 | Builders | 3 | 90
178 | 36 | Build interior | 2021-06-26 | 5 | 2021-06-30 | Builders | 1 | 90
178 | 36 | Build interior | 2021-06-26 | 5 | 2021-06-30 | Decorators | 2 | 50
179 | 36 | Fit out | 2021-07-01 | 7 | 2021-07-07 | Decorators | 5 | 50
179 | 36 | Fit out | 2021-07-01 | 7 | 2021-07-07 | Mechanical and Electrical | 5 | 80
180 | 36 | Build roof | 2021-06-24 | 3 | 2021-06-26 | Builders | 1 | 90
181 | 37 | Concrete floor | 2021-07-03 | 40 | 2021-08-11 | Concreters | 2 | 100
181 | 37 | Concrete floor | 2021-07-03 | 40 | 2021-08-11 | Ready-mix concrete | 100 | 2
182 | 37 | Build walls | 2021-07-07 | 3 | 2021-07-09 | Builders | 5 | 90
183 | 37 | Build interior | 2021-07-10 | 5 | 2021-07-14 | Builders | 3 | 90
183 | 37 | Build interior | 2021-07-10 | 5 | 2021-07-14 | Decorators | 4 | 50
184 | 37 | Fit out | 2021-07-15 | 7 | 2021-07-21 | Decorators | 6 | 50
184 | 37 | Fit out | 2021-07-15 | 7 | 2021-07-21 | Mechanical and Electrical | 6 | 80
185 | 37 | Build roof | 2021-07-08 | 3 | 2021-07-10 | Builders | 3 | 90
185 | 37 | Build roof | 2021-07-08 | 3 | 2021-07-10 | Mobile crane | 2 | 150
186 | 38 | Concrete floor | 2021-07-17 | 40 | 2021-08-25 | Concreters | 2 | 100
186 | 38 | Concrete floor | 2021-07-17 | 40 | 2021-08-25 | Ready-mix concrete | 100 | 2
187 | 38 | Build walls | 2021-07-21 | 3 | 2021-07-23 | Builders | 4 | 90
188 | 38 | Build interior | 2021-07-24 | 5 | 2021-07-28 | Builders | 1 | 90
188 | 38 | Build interior | 2021-07-24 | 5 | 2021-07-28 | Decorators | 3 | 50
189 | 38 | Fit out | 2021-07-29 | 7 | 2021-08-04 | Decorators | 6 | 50
189 | 38 | Fit out | 2021-07-29 | 7 | 2021-08-04 | Mechanical and Electrical | 6 | 80
190 | 38 | Build roof | 2021-07-22 | 3 | 2021-07-24 | Builders | 1 | 90
191 | 39 | Concrete floor | 2021-07-31 | 40 | 2021-09-08 | Concreters | 1 | 100
191 | 39 | Concrete floor | 2021-07-31 | 40 | 2021-09-08 | Ready-mix concrete | 100 | 2
192 | 39 | Build walls | 2021-08-04 | 3 | 2021-08-06 | Builders | 4 | 90
193 | 39 | Build interior | 2021-08-07 | 5 | 2021-08-11 | Builders | 2 | 90
193 | 39 | Build interior | 2021-08-07 | 5 | 2021-08-11 | Decorators | 3 | 50
194 | 39 | Fit out | 2021-08-12 | 7 | 2021-08-18 | Decorators | 6 | 50
194 | 39 | Fit out | 2021-08-12 | 7 | 2021-08-18 | Mechanical and Electrical | 7 | 80
195 | 39 | Build roof | 2021-08-05 | 3 | 2021-08-07 | Builders | 2 | 90
196 | 40 | Concrete floor | 2021-08-14 | 40 | 2021-09-22 | Concreters | 3 | 100
196 | 40 | Concrete floor | 2021-08-14 | 40 | 2021-09-22 | Ready-mix concrete | 100 | 2
197 | 40 | Build walls | 2021-08-18 | 3 | 2021-08-20 | Builders | 5 | 90
198 | 40 | Build interior | 2021-08-21 | 5 | 2021-08-25 | Builders | 2 | 90
198 | 40 | Build interior | 2021-08-21 | 5 | 2021-08-25 | Decorators | 3 | 50
199 | 40 | Fit out | 2021-08-26 | 7 | 2021-09-01 | Decorators | 5 | 50
199 | 40 | Fit out | 2021-08-26 | 7 | 2021-09-01 | Mechanical and Electrical | 6 | 80
200 | 40 | Build roof | 2021-08-19 | 3 | 2021-08-21 | Builders | 1 | 90
201 | 41 | Concrete floor | 2021-08-28 | 40 | 2021-10-06 | Concreters | 1 | 100
201 | 41 | Concrete floor | 2021-08-28 | 40 | 2021-10-06 | Ready-mix concrete | 100 | 2
202 | 41 | Build walls | 2021-09-01 | 3 | 2021-09-03 | Builders | 3 | 90
203 | 41 | Build interior | 2021-09-04 | 5 | 2021-09-08 | Builders | 3 | 90
203 | 41 | Build interior | 2021-09-04 | 5 | 2021-09-08 | Decorators | 2 | 50
204 | 41 | Fit out | 2021-09-09 | 7 | 2021-09-15 | Decorators | 5 | 50
204 | 41 | Fit out | 2021-09-09 | 7 | 2021-09-15 | Mechanical and Electrical | 6 | 80
205 | 41 | Build roof | 2021-09-02 | 3 | 2021-09-04 | Builders | 3 | 90
205 | 41 | Build roof | 2021-09-02 | 3 | 2021-09-04 | Mobile crane | 1 | 150
206 | 42 | Concrete floor | 2021-09-11 | 40 | 2021-10-20 | Concreters | 2 | 100
206 | 42 | Concrete floor | 2021-09-11 | 40 | 2021-10-20 | Ready-mix concrete | 100 | 2
207 | 42 | Build walls | 2021-09-15 | 3 | 2021-09-17 | Builders | 4 | 90
208 | 42 | Build interior | 2021-09-18 | 5 | 2021-09-22 | Builders | 1 | 90
208 | 42 | Build interior | 2021-09-18 | 5 | 2021-09-22 | Decorators | 2 | 50
209 | 42 | Fit out | 2021-09-23 | 7 | 2021-09-29 | Decorators | 4 | 50
209 | 42 | Fit out | 2021-09-23 | 7 | 2021-09-29 | Mechanical and Electrical | 5 | 80
210 | 42 | Build roof | 2021-09-16 | 3 | 2021-09-18 | Builders | 1 | 90
211 | 43 | Concrete floor | 2021-09-25 | 40 | 2021-11-03 | Concreters | 2 | 100
211 | 43 | Concrete floor | 2021-09-25 | 40 | 2021-11-03 | Ready-mix concrete | 100 | 2
212 | 43 | Build walls | 2021-09-29 | 3 | 2021-10-01 | Builders | 3 | 90
213 | 43 | Build interior | 2021-10-02 | 5 | 2021-10-06 | Builders | 1 | 90
213 | 43 | Build interior | 2021-10-02 | 5 | 2021-10-06 | Decorators | 4 | 50
214 | 43 | Fit out | 2021-10-07 | 7 | 2021-10-13 | Decorators | 4 | 50
214 | 43 | Fit out | 2021-10-07 | 7 | 2021-10-13 | Mechanical and Electrical | 7 | 80
215 | 43 | Build roof | 2021-09-30 | 3 | 2021-10-02 | Builders | 2 | 90
215 | 43 | Build roof | 2021-09-30 | 3 | 2021-10-02 | Mobile crane | 2 | 150
216 | 44 | Concrete floor | 2021-10-09 | 40 | 2021-11-17 | Concreters | 2 | 100
216 | 44 | Concrete floor | 2021-10-09 | 40 | 2021-11-17 | Ready-mix concrete | 100 | 2
217 | 44 | Build walls | 2021-10-13 | 3 | 2021-10-15 | Builders | 4 | 90
218 | 44 | Build interior | 2021-10-16 | 5 | 2021-10-20 | Builders | 2 | 90
218 | 44 | Build interior | 2021-10-16 | 5 | 2021-10-20 | Decorators | 4 | 50
219 | 44 | Fit out | 2021-10-21 | 7 | 2021-10-27 | Decorators | 4 | 50
219 | 44 | Fit out | 2021-10-21 | 7 | 2021-10-27 | Mechanical and Electrical | 5 | 80
220 | 44 | Build roof | 2021-10-14 | 3 | 2021-10-16 | Builders | 1 | 90
220 | 44 | Build roof | 2021-10-14 | 3 | 2021-10-16 | Mobile crane | 2 | 150
221 | 45 | Concrete floor | 2021-10-23 | 40 | 2021-12-01 | Concreters | 2 | 100
221 | 45 | Concrete floor | 2021-10-23 | 40 | 2021-12-01 | Ready-mix concrete | 100 | 2
222 | 45 | Build walls | 2021-10-27 | 3 | 2021-10-29 | Builders | 3 | 90
223 | 45 | Build interior | 2021-10-30 | 5 | 2021-11-03 | Builders | 2 | 90
223 | 45 | Build interior | 2021-10-30 | 5 | 2021-11-03 | Decorators | 3 | 50
224 | 45 | Fit out | 2021-11-04 | 7 | 2021-11-10 | Decorators | 4 | 50
224 | 45 | Fit out | 2021-11-04 | 7 | 2021-11-10 | Mechanical and Electrical | 5 | 80
225 | 45 | Build roof | 2021-10-28 | 3 | 2021-10-30 | Builders | 3 | 90
225 | 45 | Build roof | 2021-10-28 | 3 | 2021-10-30 | Mobile crane | 1 | 150
226 | 46 | Concrete floor | 2021-11-06 | 40 | 2021-12-15 | Concreters | 3 | 100
226 | 46 | Concrete floor | 2021-11-06 | 40 | 2021-12-15 | Ready-mix concrete | 100 | 2
227 | 46 | Build walls | 2021-11-10 | 3 | 2021-11-12 | Builders | 5 | 90
228 | 46 | Build interior | 2021-11-13 | 5 | 2021-11-17 | Builders | 2 | 90
228 | 46 | Build interior | 2021-11-13 | 5 | 2021-11-17 | Decorators | 4 | 50
229 | 46 | Fit out | 2021-11-18 | 7 | 2021-11-24 | Decorators | 6 | 50
229 | 46 | Fit out | 2021-11-18 | 7 | 2021-11-24 | Mechanical and Electrical | 5 | 80
230 | 46 | Build roof | 2021-11-11 | 3 | 2021-11-13 | Builders | 2 | 90
230 | 46 | Build roof | 2021-11-11 | 3 | 2021-11-13 | Mobile crane | 1 | 150
231 | 47 | Concrete floor | 2021-11-20 | 40 | 2021-12-29 | Concreters | 3 | 100
231 | 47 | Concrete floor | 2021-11-20 | 40 | 2021-12-29 | Ready-mix concrete | 100 | 2
232 | 47 | Build walls | 2021-11-24 | 3 | 2021-11-26 | Builders | 5 | 90
233 | 47 | Build interior | 2021-11-27 | 5 | 2021-12-01 | Builders | 3 | 90
233 | 47 | Build interior | 2021-11-27 | 5 | 2021-12-01 | Decorators | 4 | 50
234 | 47 | Fit out | 2021-12-02 | 7 | 2021-12-08 | Decorators | 6 | 50
234 | 47 | Fit out | 2021-12-02 | 7 | 2021-12-08 | Mechanical and Electrical | 7 | 80
235 | 47 | Build roof | 2021-11-25 | 3 | 2021-11-27 | Builders | 3 | 90
235 | 47 | Build roof | 2021-11-25 | 3 | 2021-11-27 | Mobile crane | 2 | 150
236 | 48 | Concrete floor | 2021-12-04 | 40 | 2022-01-12 | Concreters | 1 | 100
236 | 48 | Concrete floor | 2021-12-04 | 40 | 2022-01-12 | Ready-mix concrete | 100 | 2
237 | 48 | Build walls | 2021-12-08 | 3 | 2021-12-10 | Builders | 4 | 90
238 | 48 | Build interior | 2021-12-11 | 5 | 2021-12-15 | Builders | 3 | 90
238 | 48 | Build interior | 2021-12-11 | 5 | 2021-12-15 | Decorators | 2 | 50
239 | 48 | Fit out | 2021-12-16 | 7 | 2021-12-22 | Decorators | 4 | 50
239 | 48 | Fit out | 2021-12-16 | 7 | 2021-12-22 | Mechanical and Electrical | 7 | 80
240 | 48 | Build roof | 2021-12-09 | 3 | 2021-12-11 | Builders | 3 | 90
241 | 49 | Concrete floor | 2021-12-18 | 40 | 2022-01-26 | Concreters | 3 | 100
241 | 49 | Concrete floor | 2021-12-18 | 40 | 2022-01-26 | Ready-mix concrete | 100 | 2
242 | 49 | Build walls | 2021-12-22 | 3 | 2021-12-24 | Builders | 5 | 90
243 | 49 | Build interior | 2021-12-25 | 5 | 2021-12-29 | Builders | 3 | 90
243 | 49 | Build interior | 2021-12-25 | 5 | 2021-12-29 | Decorators | 3 | 50
244 | 49 | Fit out | 2021-12-30 | 7 | 2022-01-05 | Decorators | 4 | 50
244 | 49 | Fit out | 2021-12-30 | 7 | 2022-01-05 | Mechanical and Electrical | 5 | 80
245 | 49 | Build roof | 2021-12-23 | 3 | 2021-12-25 | Builders | 3 | 90
246 | 50 | Concrete floor | 2022-01-01 | 40 | 2022-02-09 | Concreters | 1 | 100
246 | 50 | Concrete floor | 2022-01-01 | 40 | 2022-02-09 | Ready-mix concrete | 100 | 2
247 | 50 | Build walls | 2022-01-05 | 3 | 2022-01-07 | Builders | 4 | 90
248 | 50 | Build interior | 2022-01-08 | 5 | 2022-01-12 | Builders | 1 | 90
248 | 50 | Build interior | 2022-01-08 | 5 | 2022-01-12 | Decorators | 2 | 50
249 | 50 | Fit out | 2022-01-13 | 7 | 2022-01-19 | Decorators | 6 | 50
249 | 50 | Fit out | 2022-01-13 | 7 | 2022-01-19 | Mechanical and Electrical | 6 | 80
250 | 50 | Build roof | 2022-01-06 | 3 | 2022-01-08 | Builders | 2 | 90
250 | 50 | Build roof | 2022-01-06 | 3 | 2022-01-08 | Mobile crane | 1 | 150
250 | 50 | Build roof | 2022-01-06 | 3 | 2022-01-08 | Mobile crane | 1 | 150

## Append
Activity ID | Resource | Number | Cost
1 | Concreters | 2 | 100
1 | Ready-mix concrete | 100 | 2
2 | Builders | 4 | 90
3 | Builders | 2 | 90
3 | Decorators | 3 | 50
4 | Decorators | 5 | 50
4 | Mechanical and Electrical | 6 | 80
5 | Builders | 2 | 90
5 | Mobile crane | 1 | 150
6 | Concreters | 3 | 100
6 | Ready-mix concrete | 100 | 2
7 | Builders | 4 | 90
8 | Builders | 2 | 90
8 | Decorators | 2 | 50
9 | Decorators | 6 | 50
9 | Mechanical and Electrical | 7 | 80
10 | Builders | 2 | 90
10 | Mobile crane | 2 | 150
11 | Concreters | 3 | 100
11 | Ready-mix concrete | 100 | 2
12 | Builders | 5 | 90
13 | Builders | 2 | 90
13 | Decorators | 4 | 50
14 | Decorators | 4 | 50
14 | Mechanical and Electrical | 7 | 80
15 | Builders | 1 | 90
16 | Concreters | 2 | 100
16 | Ready-mix concrete | 100 | 2
17 | Builders | 3 | 90
18 | Builders | 2 | 90
18 | Decorators | 4 | 50
19 | Decorators | 6 | 50
19 | Mechanical and Electrical | 5 | 80
20 | Builders | 1 | 90
21 | Concreters | 3 | 100
21 | Ready-mix concrete | 100 | 2
22 | Builders | 3 | 90
23 | Builders | 3 | 90
23 | Decorators | 2 | 50
24 | Decorators | 4 | 50
24 | Mechanical and Electrical | 6 | 80
25 | Builders | 2 | 90
25 | Mobile crane | 2 | 150
26 | Concreters | 2 | 100
26 | Ready-mix concrete | 100 | 2
27 | Builders | 5 | 90
28 | Builders | 2 | 90
28 | Decorators | 3 | 50
29 | Decorators | 6 | 50
29 | Mechanical and Electrical | 5 | 80
30 | Builders | 1 | 90
31 | Concreters | 2 | 100
31 | Ready-mix concrete | 100 | 2
32 | Builders | 4 | 90
33 | Builders | 2 | 90
33 | Decorators | 4 | 50
34 | Decorators | 4 | 50
34 | Mechanical and Electrical | 6 | 80
35 | Builders | 2 | 90
35 | Mobile crane | 1 | 150
36 | Concreters | 3 | 100
36 | Ready-mix concrete | 100 | 2
37 | Builders | 3 | 90
38 | Builders | 1 | 90
38 | Decorators | 2 | 50
39 | Decorators | 4 | 50
39 | Mechanical and Electrical | 7 | 80
40 | Builders | 1 | 90
41 | Concreters | 1 | 100
41 | Ready-mix concrete | 100 | 2
42 | Builders | 5 | 90
43 | Builders | 3 | 90
43 | Decorators | 2 | 50
44 | Decorators | 5 | 50
44 | Mechanical and Electrical | 5 | 80
45 | Builders | 3 | 90
45 | Mobile crane | 2 | 150
46 | Concreters | 2 | 100
46 | Ready-mix concrete | 100 | 2
47 | Builders | 4 | 90
48 | Builders | 1 | 90
48 | Decorators | 3 | 50
49 | Decorators | 5 | 50
49 | Mechanical and Electrical | 5 | 80
50 | Builders | 1 | 90
50 | Mobile crane | 2 | 150
51 | Concreters | 3 | 100
51 | Ready-mix concrete | 100 | 2
52 | Builders | 5 | 90
53 | Builders | 2 | 90
53 | Decorators | 4 | 50
54 | Decorators | 5 | 50
54 | Mechanical and Electrical | 5 | 80
55 | Builders | 2 | 90
55 | Mobile crane | 2 | 150
56 | Concreters | 3 | 100
56 | Ready-mix concrete | 100 | 2
57 | Builders | 4 | 90
58 | Builders | 1 | 90
58 | Decorators | 4 | 50
59 | Decorators | 6 | 50
59 | Mechanical and Electrical | 6 | 80
60 | Builders | 2 | 90
61 | Concreters | 1 | 100
61 | Ready-mix concrete | 100 | 2
62 | Builders | 3 | 90
63 | Builders | 3 | 90
63 | Decorators | 3 | 50
64 | Decorators | 4 | 50
64 | Mechanical and Electrical | 7 | 80
65 | Builders | 3 | 90
65 | Mobile crane | 1 | 150
66 | Concreters | 1 | 100
66 | Ready-mix concrete | 100 | 2
67 | Builders | 3 | 90
68 | Builders | 3 | 90
68 | Decorators | 4 | 50
69 | Decorators | 6 | 50
69 | Mechanical and Electrical | 7 | 80
70 | Builders | 3 | 90
70 | Mobile crane | 1 | 150
71 | Concreters | 1 | 100
71 | Ready-mix concrete | 100 | 2
72 | Builders | 4 | 90
73 | Builders | 1 | 90
73 | Decorators | 4 | 50
74 | Decorators | 5 | 50
74 | Mechanical and Electrical | 6 | 80
75 | Builders | 1 | 90
75 | Mobile crane | 2 | 150
76 | Concreters | 3 | 100
76 | Ready-mix concrete | 100 | 2
77 | Builders | 4 | 90
78 | Builders | 1 | 90
78 | Decorators | 2 | 50
79 | Decorators | 5 | 50
79 | Mechanical and Electrical | 6 | 80
80 | Builders | 1 | 90
81 | Concreters | 2 | 100
81 | Ready-mix concrete | 100 | 2
82 | Builders | 3 | 90
83 | Builders | 3 | 90
83 | Decorators | 3 | 50
84 | Decorators | 5 | 50
84 | Mechanical and Electrical | 6 | 80
85 | Builders | 1 | 90
85 | Mobile crane | 2 | 150
86 | Concreters | 3 | 100
86 | Ready-mix concrete | 100 | 2
87 | Builders | 4 | 90
88 | Builders | 2 | 90
88 | Decorators | 2 | 50
89 | Decorators | 4 | 50
89 | Mechanical and Electrical | 6 | 80
90 | Builders | 2 | 90
91 | Concreters | 2 | 100
91 | Ready-mix concrete | 100 | 2
92 | Builders | 5 | 90
93 | Builders | 3 | 90
93 | Decorators | 3 | 50
94 | Decorators | 4 | 50
94 | Mechanical and Electrical | 6 | 80
95 | Builders | 2 | 90
96 | Concreters | 2 | 100
96 | Ready-mix concrete | 100 | 2
97 | Builders | 5 | 90
98 | Builders | 1 | 90
98 | Decorators | 4 | 50
99 | Decorators | 6 | 50
99 | Mechanical and Electrical | 6 | 80
100 | Builders | 3 | 90
100 | Mobile crane | 1 | 150
101 | Concreters | 2 | 100
101 | Ready-mix concrete | 100 | 2
102 | Builders | 3 | 90
103 | Builders | 1 | 90
103 | Decorators | 2 | 50
104 | Decorators | 6 | 50
104 | Mechanical and Electrical | 7 | 80
105 | Builders | 3 | 90
105 | Mobile crane | 1 | 150
106 | Concreters | 2 | 100
106 | Ready-mix concrete | 100 | 2
107 | Builders | 4 | 90
108 | Builders | 1 | 90
108 | Decorators | 4 | 50
109 | Decorators | 5 | 50
109 | Mechanical and Electrical | 7 | 80
110 | Builders | 3 | 90
110 | Mobile crane | 1 | 150
111 | Concreters | 1 | 100
111 | Ready-mix concrete | 100 | 2
112 | Builders | 4 | 90
113 | Builders | 1 | 90
113 | Decorators | 4 | 50
114 | Decorators | 5 | 50
114 | Mechanical and Electrical | 7 | 80
115 | Builders | 3 | 90
115 | Mobile crane | 1 | 150
116 | Concreters | 2 | 100
116 | Ready-mix concrete | 100 | 2
117 | Builders | 3 | 90
118 | Builders | 2 | 90
118 | Decorators | 2 | 50
119 | Decorators | 4 | 50
119 | Mechanical and Electrical | 5 | 80
120 | Builders | 2 | 90
121 | Concreters | 3 | 100
121 | Ready-mix concrete | 100 | 2
122 | Builders | 4 | 90
123 | Builders | 1 | 90
123 | Decorators | 4 | 50
124 | Decorators | 6 | 50
124 | Mechanical and Electrical | 5 | 80
125 | Builders | 3 | 90
126 | Concreters | 2 | 100
126 | Ready-mix concrete | 100 | 2
127 | Builders | 4 | 90
128 | Builders | 3 | 90
128 | Decorators | 3 | 50
129 | Decorators | 4 | 50
129 | Mechanical and Electrical | 7 | 80
130 | Builders | 1 | 90
130 | Mobile crane | 1 | 150
131 | Concreters | 3 | 100
131 | Ready-mix concrete | 100 | 2
132 | Builders | 4 | 90
133 | Builders | 3 | 90
133 | Decorators | 2 | 50
134 | Decorators | 6 | 50
134 | Mechanical and Electrical | 6 | 80
135 | Builders | 2 | 90
135 | Mobile crane | 1 | 150
136 | Concreters | 2 | 100
136 | Ready-mix concrete | 100 | 2
137 | Builders | 3 | 90
138 | Builders | 2 | 90
138 | Decorators | 3 | 50
139 | Decorators | 4 | 50
139 | Mechanical and Electrical | 6 | 80
140 | Builders | 2 | 90
141 | Concreters | 2 | 100
141 | Ready-mix concrete | 100 | 2
142 | Builders | 3 | 90
143 | Builders | 3 | 90
143 | Decorators | 2 | 50
144 | Decorators | 4 | 50
144 | Mechanical and Electrical | 6 | 80
145 | Builders | 1 | 90
145 | Builders | 1 | 90
145 | Builders | 1 | 90
145 | Mobile crane | 1 | 150
146 | Concreters | 2 | 100
146 | Ready-mix concrete | 100 | 2
147 | Builders | 4 | 90
148 | Builders | 3 | 90
148 | Decorators | 2 | 50
149 | Decorators | 5 | 50
149 | Mechanical and Electrical | 6 | 80
150 | Builders | 2 | 90
150 | Mobile crane | 2 | 150
151 | Concreters | 1 | 100
151 | Ready-mix concrete | 100 | 2
152 | Builders | 5 | 90
153 | Builders | 1 | 90
153 | Decorators | 3 | 50
154 | Decorators | 4 | 50
154 | Mechanical and Electrical | 7 | 80
155 | Builders | 2 | 90
156 | Concreters | 1 | 100
156 | Ready-mix concrete | 100 | 2
157 | Builders | 4 | 90
158 | Builders | 1 | 90
158 | Decorators | 3 | 50
159 | Decorators | 5 | 50
159 | Mechanical and Electrical | 6 | 80
160 | Builders | 2 | 90
161 | Concreters | 1 | 100
161 | Ready-mix concrete | 100 | 2
162 | Builders | 5 | 90
163 | Builders | 1 | 90
163 | Decorators | 2 | 50
164 | Decorators | 6 | 50
164 | Mechanical and Electrical | 6 | 80
165 | Builders | 1 | 90
165 | Mobile crane | 2 | 150
166 | Concreters | 1 | 100
166 | Ready-mix concrete | 100 | 2
167 | Builders | 3 | 90
168 | Builders | 1 | 90
168 | Decorators | 4 | 50
169 | Decorators | 6 | 50
169 | Mechanical and Electrical | 7 | 80
170 | Builders | 2 | 90
170 | Mobile crane | 1 | 150
171 | Concreters | 2 | 100
171 | Ready-mix concrete | 100 | 2
172 | Builders | 4 | 90
173 | Builders | 1 | 90
173 | Decorators | 3 | 50
174 | Decorators | 6 | 50
174 | Mechanical and Electrical | 5 | 80
175 | Builders | 3 | 90
176 | Concreters | 3 | 100
176 | Ready-mix concrete | 100 | 2
177 | Builders | 3 | 90
178 | Builders | 1 | 90
178 | Decorators | 2 | 50
179 | Decorators | 5 | 50
179 | Mechanical and Electrical | 5 | 80
180 | Builders | 1 | 90
181 | Concreters | 2 | 100
181 | Ready-mix concrete | 100 | 2
182 | Builders | 5 | 90
183 | Builders | 3 | 90
183 | Decorators | 4 | 50
184 | Decorators | 6 | 50
184 | Mechanical and Electrical | 6 | 80
185 | Builders | 3 | 90
185 | Mobile crane | 2 | 150
186 | Concreters | 2 | 100
186 | Ready-mix concrete | 100 | 2
187 | Builders | 4 | 90
188 | Builders | 1 | 90
188 | Decorators | 3 | 50
189 | Decorators | 6 | 50
189 | Mechanical and Electrical | 6 | 80
190 | Builders | 1 | 90
191 | Concreters | 1 | 100
191 | Ready-mix concrete | 100 | 2
192 | Builders | 4 | 90
193 | Builders | 2 | 90
193 | Decorators | 3 | 50
194 | Decorators | 6 | 50
194 | Mechanical and Electrical | 7 | 80
195 | Builders | 2 | 90
196 | Concreters | 3 | 100
196 | Ready-mix concrete | 100 | 2
197 | Builders | 5 | 90
198 | Builders | 2 | 90
198 | Decorators | 3 | 50
199 | Decorators | 5 | 50
199 | Mechanical and Electrical | 6 | 80
200 | Builders | 1 | 90
201 | Concreters | 1 | 100
201 | Ready-mix concrete | 100 | 2
202 | Builders | 3 | 90
203 | Builders | 3 | 90
203 | Decorators | 2 | 50
204 | Decorators | 5 | 50
204 | Mechanical and Electrical | 6 | 80
205 | Builders | 3 | 90
205 | Mobile crane | 1 | 150
206 | Concreters | 2 | 100
206 | Ready-mix concrete | 100 | 2
207 | Builders | 4 | 90
208 | Builders | 1 | 90
208 | Decorators | 2 | 50
209 | Decorators | 4 | 50
209 | Mechanical and Electrical | 5 | 80
210 | Builders | 1 | 90
211 | Concreters | 2 | 100
211 | Ready-mix concrete | 100 | 2
212 | Builders | 3 | 90
213 | Builders | 1 | 90
213 | Decorators | 4 | 50
214 | Decorators | 4 | 50
214 | Mechanical and Electrical | 7 | 80
215 | Builders | 2 | 90
215 | Mobile crane | 2 | 150
216 | Concreters | 2 | 100
216 | Ready-mix concrete | 100 | 2
217 | Builders | 4 | 90
218 | Builders | 2 | 90
218 | Decorators | 4 | 50
219 | Decorators | 4 | 50
219 | Mechanical and Electrical | 5 | 80
220 | Builders | 1 | 90
220 | Mobile crane | 2 | 150
221 | Concreters | 2 | 100
221 | Ready-mix concrete | 100 | 2
222 | Builders | 3 | 90
223 | Builders | 2 | 90
223 | Decorators | 3 | 50
224 | Decorators | 4 | 50
224 | Mechanical and Electrical | 5 | 80
225 | Builders | 3 | 90
225 | Mobile crane | 1 | 150
226 | Concreters | 3 | 100
226 | Ready-mix concrete | 100 | 2
227 | Builders | 5 | 90
228 | Builders | 2 | 90
228 | Decorators | 4 | 50
229 | Decorators | 6 | 50
229 | Mechanical and Electrical | 5 | 80
230 | Builders | 2 | 90
230 | Mobile crane | 1 | 150
231 | Concreters | 3 | 100
231 | Ready-mix concrete | 100 | 2
232 | Builders | 5 | 90
233 | Builders | 3 | 90
233 | Decorators | 4 | 50
234 | Decorators | 6 | 50
234 | Mechanical and Electrical | 7 | 80
235 | Builders | 3 | 90
235 | Mobile crane | 2 | 150
236 | Concreters | 1 | 100
236 | Ready-mix concrete | 100 | 2
237 | Builders | 4 | 90
238 | Builders | 3 | 90
238 | Decorators | 2 | 50
239 | Decorators | 4 | 50
239 | Mechanical and Electrical | 7 | 80
240 | Builders | 3 | 90
241 | Concreters | 3 | 100
241 | Ready-mix concrete | 100 | 2
242 | Builders | 5 | 90
243 | Builders | 3 | 90
243 | Decorators | 3 | 50
244 | Decorators | 4 | 50
244 | Mechanical and Electrical | 5 | 80
245 | Builders | 3 | 90
246 | Concreters | 1 | 100
246 | Ready-mix concrete | 100 | 2
247 | Builders | 4 | 90
248 | Builders | 1 | 90
248 | Decorators | 2 | 50
249 | Decorators | 6 | 50
249 | Mechanical and Electrical | 6 | 80
250 | Builders | 2 | 90
250 | Mobile crane | 1 | 150
250 | Mobile crane | 1 | 150

## ProjectSchedule
Activity ID | HOUSE | TASK | START | Duration | End
1 | 1 | Concrete floor | 2020-02-15 | 40 | 2020-03-25
2 | 1 | Build walls | 2020-02-19 | 3 | 2020-02-21
3 | 1 | Build interior | 2020-02-22 | 5 | 2020-02-26
4 | 1 | Fit out | 2020-02-27 | 7 | 2020-03-04
5 | 1 | Build roof | 2020-02-20 | 3 | 2020-02-22
6 | 2 | Concrete floor | 2020-02-29 | 40 | 2020-04-08
7 | 2 | Build walls | 2020-03-04 | 3 | 2020-03-06
8 | 2 | Build interior | 2020-03-07 | 5 | 2020-03-11
9 | 2 | Fit out | 2020-03-12 | 7 | 2020-03-18
10 | 2 | Build roof | 2020-03-05 | 3 | 2020-03-07
11 | 3 | Concrete floor | 2020-03-14 | 40 | 2020-04-22
12 | 3 | Build walls | 2020-03-18 | 3 | 2020-03-20
13 | 3 | Build interior | 2020-03-21 | 5 | 2020-03-25
14 | 3 | Fit out | 2020-03-26 | 7 | 2020-04-01
15 | 3 | Build roof | 2020-03-19 | 3 | 2020-03-21
16 | 4 | Concrete floor | 2020-03-28 | 40 | 2020-05-06
17 | 4 | Build walls | 2020-04-01 | 3 | 2020-04-03
18 | 4 | Build interior | 2020-04-04 | 5 | 2020-04-08
19 | 4 | Fit out | 2020-04-09 | 7 | 2020-04-15
20 | 4 | Build roof | 2020-04-02 | 3 | 2020-04-04
21 | 5 | Concrete floor | 2020-04-11 | 40 | 2020-05-20
22 | 5 | Build walls | 2020-04-15 | 3 | 2020-04-17
23 | 5 | Build interior | 2020-04-18 | 5 | 2020-04-22
24 | 5 | Fit out | 2020-04-23 | 7 | 2020-04-29
25 | 5 | Build roof | 2020-04-16 | 3 | 2020-04-18
26 | 6 | Concrete floor | 2020-04-25 | 40 | 2020-06-03
27 | 6 | Build walls | 2020-04-29 | 3 | 2020-05-01
28 | 6 | Build interior | 2020-05-02 | 5 | 2020-05-06
29 | 6 | Fit out | 2020-05-07 | 7 | 2020-05-13
30 | 6 | Build roof | 2020-04-30 | 3 | 2020-05-02
31 | 7 | Concrete floor | 2020-05-09 | 40 | 2020-06-17
32 | 7 | Build walls | 2020-05-13 | 3 | 2020-05-15
33 | 7 | Build interior | 2020-05-16 | 5 | 2020-05-20
34 | 7 | Fit out | 2020-05-21 | 7 | 2020-05-27
35 | 7 | Build roof | 2020-05-14 | 3 | 2020-05-16
36 | 8 | Concrete floor | 2020-05-23 | 40 | 2020-07-01
37 | 8 | Build walls | 2020-05-27 | 3 | 2020-05-29
38 | 8 | Build interior | 2020-05-30 | 5 | 2020-06-03
39 | 8 | Fit out | 2020-06-04 | 7 | 2020-06-10
40 | 8 | Build roof | 2020-05-28 | 3 | 2020-05-30
41 | 9 | Concrete floor | 2020-06-06 | 40 | 2020-07-15
42 | 9 | Build walls | 2020-06-10 | 3 | 2020-06-12
43 | 9 | Build interior | 2020-06-13 | 5 | 2020-06-17
44 | 9 | Fit out | 2020-06-18 | 7 | 2020-06-24
45 | 9 | Build roof | 2020-06-11 | 3 | 2020-06-13
46 | 10 | Concrete floor | 2020-06-20 | 40 | 2020-07-29
47 | 10 | Build walls | 2020-06-24 | 3 | 2020-06-26
48 | 10 | Build interior | 2020-06-27 | 5 | 2020-07-01
49 | 10 | Fit out | 2020-07-02 | 7 | 2020-07-08
50 | 10 | Build roof | 2020-06-25 | 3 | 2020-06-27
51 | 11 | Concrete floor | 2020-07-04 | 40 | 2020-08-12
52 | 11 | Build walls | 2020-07-08 | 3 | 2020-07-10
53 | 11 | Build interior | 2020-07-11 | 5 | 2020-07-15
54 | 11 | Fit out | 2020-07-16 | 7 | 2020-07-22
55 | 11 | Build roof | 2020-07-09 | 3 | 2020-07-11
56 | 12 | Concrete floor | 2020-07-18 | 40 | 2020-08-26
57 | 12 | Build walls | 2020-07-22 | 3 | 2020-07-24
58 | 12 | Build interior | 2020-07-25 | 5 | 2020-07-29
59 | 12 | Fit out | 2020-07-30 | 7 | 2020-08-05
60 | 12 | Build roof | 2020-07-23 | 3 | 2020-07-25
61 | 13 | Concrete floor | 2020-08-01 | 40 | 2020-09-09
62 | 13 | Build walls | 2020-08-05 | 3 | 2020-08-07
63 | 13 | Build interior | 2020-08-08 | 5 | 2020-08-12
64 | 13 | Fit out | 2020-08-13 | 7 | 2020-08-19
65 | 13 | Build roof | 2020-08-06 | 3 | 2020-08-08
66 | 14 | Concrete floor | 2020-08-15 | 40 | 2020-09-23
67 | 14 | Build walls | 2020-08-19 | 3 | 2020-08-21
68 | 14 | Build interior | 2020-08-22 | 5 | 2020-08-26
69 | 14 | Fit out | 2020-08-27 | 7 | 2020-09-02
70 | 14 | Build roof | 2020-08-20 | 3 | 2020-08-22
71 | 15 | Concrete floor | 2020-08-29 | 40 | 2020-10-07
72 | 15 | Build walls | 2020-09-02 | 3 | 2020-09-04
73 | 15 | Build interior | 2020-09-05 | 5 | 2020-09-09
74 | 15 | Fit out | 2020-09-10 | 7 | 2020-09-16
75 | 15 | Build roof | 2020-09-03 | 3 | 2020-09-05
76 | 16 | Concrete floor | 2020-09-12 | 40 | 2020-10-21
77 | 16 | Build walls | 2020-09-16 | 3 | 2020-09-18
78 | 16 | Build interior | 2020-09-19 | 5 | 2020-09-23
79 | 16 | Fit out | 2020-09-24 | 7 | 2020-09-30
80 | 16 | Build roof | 2020-09-17 | 3 | 2020-09-19
81 | 17 | Concrete floor | 2020-09-26 | 40 | 2020-11-04
82 | 17 | Build walls | 2020-09-30 | 3 | 2020-10-02
83 | 17 | Build interior | 2020-10-03 | 5 | 2020-10-07
84 | 17 | Fit out | 2020-10-08 | 7 | 2020-10-14
85 | 17 | Build roof | 2020-10-01 | 3 | 2020-10-03
86 | 18 | Concrete floor | 2020-10-10 | 40 | 2020-11-18
87 | 18 | Build walls | 2020-10-14 | 3 | 2020-10-16
88 | 18 | Build interior | 2020-10-17 | 5 | 2020-10-21
89 | 18 | Fit out | 2020-10-22 | 7 | 2020-10-28
90 | 18 | Build roof | 2020-10-15 | 3 | 2020-10-17
91 | 19 | Concrete floor | 2020-10-24 | 40 | 2020-12-02
92 | 19 | Build walls | 2020-10-28 | 3 | 2020-10-30
93 | 19 | Build interior | 2020-10-31 | 5 | 2020-11-04
94 | 19 | Fit out | 2020-11-05 | 7 | 2020-11-11
95 | 19 | Build roof | 2020-10-29 | 3 | 2020-10-31
96 | 20 | Concrete floor | 2020-11-07 | 40 | 2020-12-16
97 | 20 | Build walls | 2020-11-11 | 3 | 2020-11-13
98 | 20 | Build interior | 2020-11-14 | 5 | 2020-11-18
99 | 20 | Fit out | 2020-11-19 | 7 | 2020-11-25
100 | 20 | Build roof | 2020-11-12 | 3 | 2020-11-14
101 | 21 | Concrete floor | 2020-11-21 | 40 | 2020-12-30
102 | 21 | Build walls | 2020-11-25 | 3 | 2020-11-27
103 | 21 | Build interior | 2020-11-28 | 5 | 2020-12-02
104 | 21 | Fit out | 2020-12-03 | 7 | 2020-12-09
105 | 21 | Build roof | 2020-11-26 | 3 | 2020-11-28
106 | 22 | Concrete floor | 2020-12-05 | 40 | 2021-01-13
107 | 22 | Build walls | 2020-12-09 | 3 | 2020-12-11
108 | 22 | Build interior | 2020-12-12 | 5 | 2020-12-16
109 | 22 | Fit out | 2020-12-17 | 7 | 2020-12-23
110 | 22 | Build roof | 2020-12-10 | 3 | 2020-12-12
111 | 23 | Concrete floor | 2020-12-19 | 40 | 2021-01-27
112 | 23 | Build walls | 2020-12-23 | 3 | 2020-12-25
113 | 23 | Build interior | 2020-12-26 | 5 | 2020-12-30
114 | 23 | Fit out | 2020-12-31 | 7 | 2021-01-06
115 | 23 | Build roof | 2020-12-24 | 3 | 2020-12-26
116 | 24 | Concrete floor | 2021-01-02 | 40 | 2021-02-10
117 | 24 | Build walls | 2021-01-06 | 3 | 2021-01-08
118 | 24 | Build interior | 2021-01-09 | 5 | 2021-01-13
119 | 24 | Fit out | 2021-01-14 | 7 | 2021-01-20
120 | 24 | Build roof | 2021-01-07 | 3 | 2021-01-09
121 | 25 | Concrete floor | 2021-01-16 | 40 | 2021-02-24
122 | 25 | Build walls | 2021-01-20 | 3 | 2021-01-22
123 | 25 | Build interior | 2021-01-23 | 5 | 2021-01-27
124 | 25 | Fit out | 2021-01-28 | 7 | 2021-02-03
125 | 25 | Build roof | 2021-01-21 | 3 | 2021-01-23
126 | 26 | Concrete floor | 2021-01-30 | 40 | 2021-03-10
127 | 26 | Build walls | 2021-02-03 | 3 | 2021-02-05
128 | 26 | Build interior | 2021-02-06 | 5 | 2021-02-10
129 | 26 | Fit out | 2021-02-11 | 7 | 2021-02-17
130 | 26 | Build roof | 2021-02-04 | 3 | 2021-02-06
131 | 27 | Concrete floor | 2021-02-13 | 40 | 2021-03-24
132 | 27 | Build walls | 2021-02-17 | 3 | 2021-02-19
133 | 27 | Build interior | 2021-02-20 | 5 | 2021-02-24
134 | 27 | Fit out | 2021-02-25 | 7 | 2021-03-03
135 | 27 | Build roof | 2021-02-18 | 3 | 2021-02-20
136 | 28 | Concrete floor | 2021-02-27 | 40 | 2021-04-07
137 | 28 | Build walls | 2021-03-03 | 3 | 2021-03-05
138 | 28 | Build interior | 2021-03-06 | 5 | 2021-03-10
139 | 28 | Fit out | 2021-03-11 | 7 | 2021-03-17
140 | 28 | Build roof | 2021-03-04 | 3 | 2021-03-06
141 | 29 | Concrete floor | 2021-03-13 | 40 | 2021-04-21
142 | 29 | Build walls | 2021-03-17 | 3 | 2021-03-19
143 | 29 | Build interior | 2021-03-20 | 5 | 2021-03-24
144 | 29 | Fit out | 2021-03-25 | 7 | 2021-03-31
145 | 29 | Build roof | 2021-03-18 | 3 | 2021-03-20
146 | 30 | Concrete floor | 2021-03-27 | 40 | 2021-05-05
147 | 30 | Build walls | 2021-03-31 | 3 | 2021-04-02
148 | 30 | Build interior | 2021-04-03 | 5 | 2021-04-07
149 | 30 | Fit out | 2021-04-08 | 7 | 2021-04-14
150 | 30 | Build roof | 2021-04-01 | 3 | 2021-04-03
151 | 31 | Concrete floor | 2021-04-10 | 40 | 2021-05-19
152 | 31 | Build walls | 2021-04-14 | 3 | 2021-04-16
153 | 31 | Build interior | 2021-04-17 | 5 | 2021-04-21
154 | 31 | Fit out | 2021-04-22 | 7 | 2021-04-28
155 | 31 | Build roof | 2021-04-15 | 3 | 2021-04-17
156 | 32 | Concrete floor | 2021-04-24 | 40 | 2021-06-02
157 | 32 | Build walls | 2021-04-28 | 3 | 2021-04-30
158 | 32 | Build interior | 2021-05-01 | 5 | 2021-05-05
159 | 32 | Fit out | 2021-05-06 | 7 | 2021-05-12
160 | 32 | Build roof | 2021-04-29 | 3 | 2021-05-01
161 | 33 | Concrete floor | 2021-05-08 | 40 | 2021-06-16
162 | 33 | Build walls | 2021-05-12 | 3 | 2021-05-14
163 | 33 | Build interior | 2021-05-15 | 5 | 2021-05-19
164 | 33 | Fit out | 2021-05-20 | 7 | 2021-05-26
165 | 33 | Build roof | 2021-05-13 | 3 | 2021-05-15
166 | 34 | Concrete floor | 2021-05-22 | 40 | 2021-06-30
167 | 34 | Build walls | 2021-05-26 | 3 | 2021-05-28
168 | 34 | Build interior | 2021-05-29 | 5 | 2021-06-02
169 | 34 | Fit out | 2021-06-03 | 7 | 2021-06-09
170 | 34 | Build roof | 2021-05-27 | 3 | 2021-05-29
171 | 35 | Concrete floor | 2021-06-05 | 40 | 2021-07-14
172 | 35 | Build walls | 2021-06-09 | 3 | 2021-06-11
173 | 35 | Build interior | 2021-06-12 | 5 | 2021-06-16
174 | 35 | Fit out | 2021-06-17 | 7 | 2021-06-23
175 | 35 | Build roof | 2021-06-10 | 3 | 2021-06-12
176 | 36 | Concrete floor | 2021-06-19 | 40 | 2021-07-28
177 | 36 | Build walls | 2021-06-23 | 3 | 2021-06-25
178 | 36 | Build interior | 2021-06-26 | 5 | 2021-06-30
179 | 36 | Fit out | 2021-07-01 | 7 | 2021-07-07
180 | 36 | Build roof | 2021-06-24 | 3 | 2021-06-26
181 | 37 | Concrete floor | 2021-07-03 | 40 | 2021-08-11
182 | 37 | Build walls | 2021-07-07 | 3 | 2021-07-09
183 | 37 | Build interior | 2021-07-10 | 5 | 2021-07-14
184 | 37 | Fit out | 2021-07-15 | 7 | 2021-07-21
185 | 37 | Build roof | 2021-07-08 | 3 | 2021-07-10
186 | 38 | Concrete floor | 2021-07-17 | 40 | 2021-08-25
187 | 38 | Build walls | 2021-07-21 | 3 | 2021-07-23
188 | 38 | Build interior | 2021-07-24 | 5 | 2021-07-28
189 | 38 | Fit out | 2021-07-29 | 7 | 2021-08-04
190 | 38 | Build roof | 2021-07-22 | 3 | 2021-07-24
191 | 39 | Concrete floor | 2021-07-31 | 40 | 2021-09-08
192 | 39 | Build walls | 2021-08-04 | 3 | 2021-08-06
193 | 39 | Build interior | 2021-08-07 | 5 | 2021-08-11
194 | 39 | Fit out | 2021-08-12 | 7 | 2021-08-18
195 | 39 | Build roof | 2021-08-05 | 3 | 2021-08-07
196 | 40 | Concrete floor | 2021-08-14 | 40 | 2021-09-22
197 | 40 | Build walls | 2021-08-18 | 3 | 2021-08-20
198 | 40 | Build interior | 2021-08-21 | 5 | 2021-08-25
199 | 40 | Fit out | 2021-08-26 | 7 | 2021-09-01
200 | 40 | Build roof | 2021-08-19 | 3 | 2021-08-21
201 | 41 | Concrete floor | 2021-08-28 | 40 | 2021-10-06
202 | 41 | Build walls | 2021-09-01 | 3 | 2021-09-03
203 | 41 | Build interior | 2021-09-04 | 5 | 2021-09-08
204 | 41 | Fit out | 2021-09-09 | 7 | 2021-09-15
205 | 41 | Build roof | 2021-09-02 | 3 | 2021-09-04
206 | 42 | Concrete floor | 2021-09-11 | 40 | 2021-10-20
207 | 42 | Build walls | 2021-09-15 | 3 | 2021-09-17
208 | 42 | Build interior | 2021-09-18 | 5 | 2021-09-22
209 | 42 | Fit out | 2021-09-23 | 7 | 2021-09-29
210 | 42 | Build roof | 2021-09-16 | 3 | 2021-09-18
211 | 43 | Concrete floor | 2021-09-25 | 40 | 2021-11-03
212 | 43 | Build walls | 2021-09-29 | 3 | 2021-10-01
213 | 43 | Build interior | 2021-10-02 | 5 | 2021-10-06
214 | 43 | Fit out | 2021-10-07 | 7 | 2021-10-13
215 | 43 | Build roof | 2021-09-30 | 3 | 2021-10-02
216 | 44 | Concrete floor | 2021-10-09 | 40 | 2021-11-17
217 | 44 | Build walls | 2021-10-13 | 3 | 2021-10-15
218 | 44 | Build interior | 2021-10-16 | 5 | 2021-10-20
219 | 44 | Fit out | 2021-10-21 | 7 | 2021-10-27
220 | 44 | Build roof | 2021-10-14 | 3 | 2021-10-16
221 | 45 | Concrete floor | 2021-10-23 | 40 | 2021-12-01
222 | 45 | Build walls | 2021-10-27 | 3 | 2021-10-29
223 | 45 | Build interior | 2021-10-30 | 5 | 2021-11-03
224 | 45 | Fit out | 2021-11-04 | 7 | 2021-11-10
225 | 45 | Build roof | 2021-10-28 | 3 | 2021-10-30
226 | 46 | Concrete floor | 2021-11-06 | 40 | 2021-12-15
227 | 46 | Build walls | 2021-11-10 | 3 | 2021-11-12
228 | 46 | Build interior | 2021-11-13 | 5 | 2021-11-17
229 | 46 | Fit out | 2021-11-18 | 7 | 2021-11-24
230 | 46 | Build roof | 2021-11-11 | 3 | 2021-11-13
231 | 47 | Concrete floor | 2021-11-20 | 40 | 2021-12-29
232 | 47 | Build walls | 2021-11-24 | 3 | 2021-11-26
233 | 47 | Build interior | 2021-11-27 | 5 | 2021-12-01
234 | 47 | Fit out | 2021-12-02 | 7 | 2021-12-08
235 | 47 | Build roof | 2021-11-25 | 3 | 2021-11-27
236 | 48 | Concrete floor | 2021-12-04 | 40 | 2022-01-12
237 | 48 | Build walls | 2021-12-08 | 3 | 2021-12-10
238 | 48 | Build interior | 2021-12-11 | 5 | 2021-12-15
239 | 48 | Fit out | 2021-12-16 | 7 | 2021-12-22
240 | 48 | Build roof | 2021-12-09 | 3 | 2021-12-11
241 | 49 | Concrete floor | 2021-12-18 | 40 | 2022-01-26
242 | 49 | Build walls | 2021-12-22 | 3 | 2021-12-24
243 | 49 | Build interior | 2021-12-25 | 5 | 2021-12-29
244 | 49 | Fit out | 2021-12-30 | 7 | 2022-01-05
245 | 49 | Build roof | 2021-12-23 | 3 | 2021-12-25
246 | 50 | Concrete floor | 2022-01-01 | 40 | 2022-02-09
247 | 50 | Build walls | 2022-01-05 | 3 | 2022-01-07
248 | 50 | Build interior | 2022-01-08 | 5 | 2022-01-12
249 | 50 | Fit out | 2022-01-13 | 7 | 2022-01-19
250 | 50 | Build roof | 2022-01-06 | 3 | 2022-01-08

## Part2
Activity ID | Resource | Number | Cost
145 | Mobile crane | 1 | 150
146 | Concreters | 2 | 100
146 | Ready-mix concrete | 100 | 2
147 | Builders | 4 | 90
148 | Builders | 3 | 90
148 | Decorators | 2 | 50
149 | Decorators | 5 | 50
149 | Mechanical and Electrical | 6 | 80
150 | Builders | 2 | 90
150 | Mobile crane | 2 | 150
151 | Concreters | 1 | 100
151 | Ready-mix concrete | 100 | 2
152 | Builders | 5 | 90
153 | Builders | 1 | 90
153 | Decorators | 3 | 50
154 | Decorators | 4 | 50
154 | Mechanical and Electrical | 7 | 80
155 | Builders | 2 | 90
156 | Concreters | 1 | 100
156 | Ready-mix concrete | 100 | 2
157 | Builders | 4 | 90
158 | Builders | 1 | 90
158 | Decorators | 3 | 50
159 | Decorators | 5 | 50
159 | Mechanical and Electrical | 6 | 80
160 | Builders | 2 | 90
161 | Concreters | 1 | 100
161 | Ready-mix concrete | 100 | 2
162 | Builders | 5 | 90
163 | Builders | 1 | 90
163 | Decorators | 2 | 50
164 | Decorators | 6 | 50
164 | Mechanical and Electrical | 6 | 80
165 | Builders | 1 | 90
165 | Mobile crane | 2 | 150
166 | Concreters | 1 | 100
166 | Ready-mix concrete | 100 | 2
167 | Builders | 3 | 90
168 | Builders | 1 | 90
168 | Decorators | 4 | 50
169 | Decorators | 6 | 50
169 | Mechanical and Electrical | 7 | 80
170 | Builders | 2 | 90
170 | Mobile crane | 1 | 150
171 | Concreters | 2 | 100
171 | Ready-mix concrete | 100 | 2
172 | Builders | 4 | 90
173 | Builders | 1 | 90
173 | Decorators | 3 | 50
174 | Decorators | 6 | 50
174 | Mechanical and Electrical | 5 | 80
175 | Builders | 3 | 90
176 | Concreters | 3 | 100
176 | Ready-mix concrete | 100 | 2
177 | Builders | 3 | 90
178 | Builders | 1 | 90
178 | Decorators | 2 | 50
179 | Decorators | 5 | 50
179 | Mechanical and Electrical | 5 | 80
180 | Builders | 1 | 90
181 | Concreters | 2 | 100
181 | Ready-mix concrete | 100 | 2
182 | Builders | 5 | 90
183 | Builders | 3 | 90
183 | Decorators | 4 | 50
184 | Decorators | 6 | 50
184 | Mechanical and Electrical | 6 | 80
185 | Builders | 3 | 90
185 | Mobile crane | 2 | 150
186 | Concreters | 2 | 100
186 | Ready-mix concrete | 100 | 2
187 | Builders | 4 | 90
188 | Builders | 1 | 90
188 | Decorators | 3 | 50
189 | Decorators | 6 | 50
189 | Mechanical and Electrical | 6 | 80
190 | Builders | 1 | 90
191 | Concreters | 1 | 100
191 | Ready-mix concrete | 100 | 2
192 | Builders | 4 | 90
193 | Builders | 2 | 90
193 | Decorators | 3 | 50
194 | Decorators | 6 | 50
194 | Mechanical and Electrical | 7 | 80
195 | Builders | 2 | 90
196 | Concreters | 3 | 100
196 | Ready-mix concrete | 100 | 2
197 | Builders | 5 | 90
198 | Builders | 2 | 90
198 | Decorators | 3 | 50
199 | Decorators | 5 | 50
199 | Mechanical and Electrical | 6 | 80
200 | Builders | 1 | 90
201 | Concreters | 1 | 100
201 | Ready-mix concrete | 100 | 2
202 | Builders | 3 | 90
203 | Builders | 3 | 90
203 | Decorators | 2 | 50
204 | Decorators | 5 | 50
204 | Mechanical and Electrical | 6 | 80
205 | Builders | 3 | 90
205 | Mobile crane | 1 | 150
206 | Concreters | 2 | 100
206 | Ready-mix concrete | 100 | 2
207 | Builders | 4 | 90
208 | Builders | 1 | 90
208 | Decorators | 2 | 50
209 | Decorators | 4 | 50
209 | Mechanical and Electrical | 5 | 80
210 | Builders | 1 | 90
211 | Concreters | 2 | 100
211 | Ready-mix concrete | 100 | 2
212 | Builders | 3 | 90
213 | Builders | 1 | 90
213 | Decorators | 4 | 50
214 | Decorators | 4 | 50
214 | Mechanical and Electrical | 7 | 80
215 | Builders | 2 | 90
215 | Mobile crane | 2 | 150
216 | Concreters | 2 | 100
216 | Ready-mix concrete | 100 | 2
217 | Builders | 4 | 90
218 | Builders | 2 | 90
218 | Decorators | 4 | 50
219 | Decorators | 4 | 50
219 | Mechanical and Electrical | 5 | 80
220 | Builders | 1 | 90
220 | Mobile crane | 2 | 150
221 | Concreters | 2 | 100
221 | Ready-mix concrete | 100 | 2
222 | Builders | 3 | 90
223 | Builders | 2 | 90
223 | Decorators | 3 | 50
224 | Decorators | 4 | 50
224 | Mechanical and Electrical | 5 | 80
225 | Builders | 3 | 90
225 | Mobile crane | 1 | 150
226 | Concreters | 3 | 100
226 | Ready-mix concrete | 100 | 2
227 | Builders | 5 | 90
228 | Builders | 2 | 90
228 | Decorators | 4 | 50
229 | Decorators | 6 | 50
229 | Mechanical and Electrical | 5 | 80
230 | Builders | 2 | 90
230 | Mobile crane | 1 | 150
231 | Concreters | 3 | 100
231 | Ready-mix concrete | 100 | 2
232 | Builders | 5 | 90
233 | Builders | 3 | 90
233 | Decorators | 4 | 50
234 | Decorators | 6 | 50
234 | Mechanical and Electrical | 7 | 80
235 | Builders | 3 | 90
235 | Mobile crane | 2 | 150
236 | Concreters | 1 | 100
236 | Ready-mix concrete | 100 | 2
237 | Builders | 4 | 90
238 | Builders | 3 | 90
238 | Decorators | 2 | 50
239 | Decorators | 4 | 50
239 | Mechanical and Electrical | 7 | 80
240 | Builders | 3 | 90
241 | Concreters | 3 | 100
241 | Ready-mix concrete | 100 | 2
242 | Builders | 5 | 90
243 | Builders | 3 | 90
243 | Decorators | 3 | 50
244 | Decorators | 4 | 50
244 | Mechanical and Electrical | 5 | 80
245 | Builders | 3 | 90
246 | Concreters | 1 | 100
246 | Ready-mix concrete | 100 | 2
247 | Builders | 4 | 90
248 | Builders | 1 | 90
248 | Decorators | 2 | 50
249 | Decorators | 6 | 50
249 | Mechanical and Electrical | 6 | 80
250 | Builders | 2 | 90
250 | Mobile crane | 1 | 150
250 | Mobile crane | 1 | 150

## Part1
Activity ID | Resource | Number | Cost
1 | Concreters | 2 | 100
1 | Ready-mix concrete | 100 | 2
2 | Builders | 4 | 90
3 | Builders | 2 | 90
3 | Decorators | 3 | 50
4 | Decorators | 5 | 50
4 | Mechanical and Electrical | 6 | 80
5 | Builders | 2 | 90
5 | Mobile crane | 1 | 150
6 | Concreters | 3 | 100
6 | Ready-mix concrete | 100 | 2
7 | Builders | 4 | 90
8 | Builders | 2 | 90
8 | Decorators | 2 | 50
9 | Decorators | 6 | 50
9 | Mechanical and Electrical | 7 | 80
10 | Builders | 2 | 90
10 | Mobile crane | 2 | 150
11 | Concreters | 3 | 100
11 | Ready-mix concrete | 100 | 2
12 | Builders | 5 | 90
13 | Builders | 2 | 90
13 | Decorators | 4 | 50
14 | Decorators | 4 | 50
14 | Mechanical and Electrical | 7 | 80
15 | Builders | 1 | 90
16 | Concreters | 2 | 100
16 | Ready-mix concrete | 100 | 2
17 | Builders | 3 | 90
18 | Builders | 2 | 90
18 | Decorators | 4 | 50
19 | Decorators | 6 | 50
19 | Mechanical and Electrical | 5 | 80
20 | Builders | 1 | 90
21 | Concreters | 3 | 100
21 | Ready-mix concrete | 100 | 2
22 | Builders | 3 | 90
23 | Builders | 3 | 90
23 | Decorators | 2 | 50
24 | Decorators | 4 | 50
24 | Mechanical and Electrical | 6 | 80
25 | Builders | 2 | 90
25 | Mobile crane | 2 | 150
26 | Concreters | 2 | 100
26 | Ready-mix concrete | 100 | 2
27 | Builders | 5 | 90
28 | Builders | 2 | 90
28 | Decorators | 3 | 50
29 | Decorators | 6 | 50
29 | Mechanical and Electrical | 5 | 80
30 | Builders | 1 | 90
31 | Concreters | 2 | 100
31 | Ready-mix concrete | 100 | 2
32 | Builders | 4 | 90
33 | Builders | 2 | 90
33 | Decorators | 4 | 50
34 | Decorators | 4 | 50
34 | Mechanical and Electrical | 6 | 80
35 | Builders | 2 | 90
35 | Mobile crane | 1 | 150
36 | Concreters | 3 | 100
36 | Ready-mix concrete | 100 | 2
37 | Builders | 3 | 90
38 | Builders | 1 | 90
38 | Decorators | 2 | 50
39 | Decorators | 4 | 50
39 | Mechanical and Electrical | 7 | 80
40 | Builders | 1 | 90
41 | Concreters | 1 | 100
41 | Ready-mix concrete | 100 | 2
42 | Builders | 5 | 90
43 | Builders | 3 | 90
43 | Decorators | 2 | 50
44 | Decorators | 5 | 50
44 | Mechanical and Electrical | 5 | 80
45 | Builders | 3 | 90
45 | Mobile crane | 2 | 150
46 | Concreters | 2 | 100
46 | Ready-mix concrete | 100 | 2
47 | Builders | 4 | 90
48 | Builders | 1 | 90
48 | Decorators | 3 | 50
49 | Decorators | 5 | 50
49 | Mechanical and Electrical | 5 | 80
50 | Builders | 1 | 90
50 | Mobile crane | 2 | 150
51 | Concreters | 3 | 100
51 | Ready-mix concrete | 100 | 2
52 | Builders | 5 | 90
53 | Builders | 2 | 90
53 | Decorators | 4 | 50
54 | Decorators | 5 | 50
54 | Mechanical and Electrical | 5 | 80
55 | Builders | 2 | 90
55 | Mobile crane | 2 | 150
56 | Concreters | 3 | 100
56 | Ready-mix concrete | 100 | 2
57 | Builders | 4 | 90
58 | Builders | 1 | 90
58 | Decorators | 4 | 50
59 | Decorators | 6 | 50
59 | Mechanical and Electrical | 6 | 80
60 | Builders | 2 | 90
61 | Concreters | 1 | 100
61 | Ready-mix concrete | 100 | 2
62 | Builders | 3 | 90
63 | Builders | 3 | 90
63 | Decorators | 3 | 50
64 | Decorators | 4 | 50
64 | Mechanical and Electrical | 7 | 80
65 | Builders | 3 | 90
65 | Mobile crane | 1 | 150
66 | Concreters | 1 | 100
66 | Ready-mix concrete | 100 | 2
67 | Builders | 3 | 90
68 | Builders | 3 | 90
68 | Decorators | 4 | 50
69 | Decorators | 6 | 50
69 | Mechanical and Electrical | 7 | 80
70 | Builders | 3 | 90
70 | Mobile crane | 1 | 150
71 | Concreters | 1 | 100
71 | Ready-mix concrete | 100 | 2
72 | Builders | 4 | 90
73 | Builders | 1 | 90
73 | Decorators | 4 | 50
74 | Decorators | 5 | 50
74 | Mechanical and Electrical | 6 | 80
75 | Builders | 1 | 90
75 | Mobile crane | 2 | 150
76 | Concreters | 3 | 100
76 | Ready-mix concrete | 100 | 2
77 | Builders | 4 | 90
78 | Builders | 1 | 90
78 | Decorators | 2 | 50
79 | Decorators | 5 | 50
79 | Mechanical and Electrical | 6 | 80
80 | Builders | 1 | 90
81 | Concreters | 2 | 100
81 | Ready-mix concrete | 100 | 2
82 | Builders | 3 | 90
83 | Builders | 3 | 90
83 | Decorators | 3 | 50
84 | Decorators | 5 | 50
84 | Mechanical and Electrical | 6 | 80
85 | Builders | 1 | 90
85 | Mobile crane | 2 | 150
86 | Concreters | 3 | 100
86 | Ready-mix concrete | 100 | 2
87 | Builders | 4 | 90
88 | Builders | 2 | 90
88 | Decorators | 2 | 50
89 | Decorators | 4 | 50
89 | Mechanical and Electrical | 6 | 80
90 | Builders | 2 | 90
91 | Concreters | 2 | 100
91 | Ready-mix concrete | 100 | 2
92 | Builders | 5 | 90
93 | Builders | 3 | 90
93 | Decorators | 3 | 50
94 | Decorators | 4 | 50
94 | Mechanical and Electrical | 6 | 80
95 | Builders | 2 | 90
96 | Concreters | 2 | 100
96 | Ready-mix concrete | 100 | 2
97 | Builders | 5 | 90
98 | Builders | 1 | 90
98 | Decorators | 4 | 50
99 | Decorators | 6 | 50
99 | Mechanical and Electrical | 6 | 80
100 | Builders | 3 | 90
100 | Mobile crane | 1 | 150
101 | Concreters | 2 | 100
101 | Ready-mix concrete | 100 | 2
102 | Builders | 3 | 90
103 | Builders | 1 | 90
103 | Decorators | 2 | 50
104 | Decorators | 6 | 50
104 | Mechanical and Electrical | 7 | 80
105 | Builders | 3 | 90
105 | Mobile crane | 1 | 150
106 | Concreters | 2 | 100
106 | Ready-mix concrete | 100 | 2
107 | Builders | 4 | 90
108 | Builders | 1 | 90
108 | Decorators | 4 | 50
109 | Decorators | 5 | 50
109 | Mechanical and Electrical | 7 | 80
110 | Builders | 3 | 90
110 | Mobile crane | 1 | 150
111 | Concreters | 1 | 100
111 | Ready-mix concrete | 100 | 2
112 | Builders | 4 | 90
113 | Builders | 1 | 90
113 | Decorators | 4 | 50
114 | Decorators | 5 | 50
114 | Mechanical and Electrical | 7 | 80
115 | Builders | 3 | 90
115 | Mobile crane | 1 | 150
116 | Concreters | 2 | 100
116 | Ready-mix concrete | 100 | 2
117 | Builders | 3 | 90
118 | Builders | 2 | 90
118 | Decorators | 2 | 50
119 | Decorators | 4 | 50
119 | Mechanical and Electrical | 5 | 80
120 | Builders | 2 | 90
121 | Concreters | 3 | 100
121 | Ready-mix concrete | 100 | 2
122 | Builders | 4 | 90
123 | Builders | 1 | 90
123 | Decorators | 4 | 50
124 | Decorators | 6 | 50
124 | Mechanical and Electrical | 5 | 80
125 | Builders | 3 | 90
126 | Concreters | 2 | 100
126 | Ready-mix concrete | 100 | 2
127 | Builders | 4 | 90
128 | Builders | 3 | 90
128 | Decorators | 3 | 50
129 | Decorators | 4 | 50
129 | Mechanical and Electrical | 7 | 80
130 | Builders | 1 | 90
130 | Mobile crane | 1 | 150
131 | Concreters | 3 | 100
131 | Ready-mix concrete | 100 | 2
132 | Builders | 4 | 90
133 | Builders | 3 | 90
133 | Decorators | 2 | 50
134 | Decorators | 6 | 50
134 | Mechanical and Electrical | 6 | 80
135 | Builders | 2 | 90
135 | Mobile crane | 1 | 150
136 | Concreters | 2 | 100
136 | Ready-mix concrete | 100 | 2
137 | Builders | 3 | 90
138 | Builders | 2 | 90
138 | Decorators | 3 | 50
139 | Decorators | 4 | 50
139 | Mechanical and Electrical | 6 | 80
140 | Builders | 2 | 90
141 | Concreters | 2 | 100
141 | Ready-mix concrete | 100 | 2
142 | Builders | 3 | 90
143 | Builders | 3 | 90
143 | Decorators | 2 | 50
144 | Decorators | 4 | 50
144 | Mechanical and Electrical | 6 | 80
145 | Builders | 1 | 90
145 | Builders | 1 | 90
145 | Builders | 1 | 90